## Intro
Moray Local Development Plan
Moray Local Development Plan Action Programme
This Action Programme supports the delivery of the Moray Local Development Plan. Section 21 of the Planning etc (Scotland) Act 2006 requires Planning Authorities to prepare an Action Programme. The Action Programme sets out the actions that are necessary to implement the strategy and polices of the plan. The Action Programme sets out • A list of actions required to deliver each of the plan’s policies and proposals • The name of the person who will carry out the action and • The indicative timescale for carrying out each action The Moray Local Development Plan Action Programme does not repeat the requirements set out in the designation or policy text. The Action Programme focuses on the actions required to overcome key constraints and issues that require joint or co-ordinated action from several parties or sites. The Moray Local Development Plan Action Programme is in four parts 1. Vision Actions 2. Policy Actions 3. Essential Settlement Infrastructure 4. Site/Settlement Actions Circular 1/2009 requires Planning Authorities to consult and consider the views of the Key Agencies, the Scottish Ministers, and anyone specified in the Action Programme. The Action Programme has been prepared initially from consultation responses to bid proposals and the Main Issues Report. Further consultation was undertaken with internal and external stakeholders as part of the consultation on the Proposed Moray Local Development Plan. Amendments to the Action Programme have been made to reflect comments made by consultees. The Action Programme will be updated every two years. A “traffic light” coding has also been added to the final column to give an overall indication on progress: • Red-sites/actions in danger of non-delivery; • Amber- sites/actions where little happening but no specific risk to non-development; • Green – sites/actions being actively progressed. A “C” has been added to actions that are complete or sites that are under construction.
Abbreviations
HIE – Highlands and Islands Enterprise | MC Lands and Parks – Moray Council Lands and Parks
HiTrans – Highlands and Islands Transportation | MC Legal – Moray Council Legal Services
MC Consultancy – Moray Council Consultancy | MC Trans – Moray Council Transportation
MC Dev Mgt – Moray Council Development Management | MES – Moray Economic Strategy
MC Dev Plans – Moray Council Development Plans | MOD/DIO – Ministry of Defence/ Defence Infrastructure Organisation
MC Economic Dev – Moray Council Economic Development | LDP – Local Development Plan
MC Education – Moray Council Education and Social Care | Scottish Gov’t – The Scottish Government
MC Estates – Moray Council Estate Services | SEPA – Scottish Environment Protection Agency
MC Flood – Moray Council Flood Risk Management | SNH – Scottish Natural Heritage
MC Housing – Moray Council Housing | SG - Supplementary Guidance

## Vision
1. Vision Actions
Vision | Action
A growing population, which retains more of its younger people and attracts new residents to the area. | LDP supports this aim by identifying housing land designations to support a growing population.
LDP supports this aim by identifying employment land designations to support a growing economy.
LDP supports this aim through the Primary Policy PP1 Sustainable Economic Growth which supports proposals that assist in the delivery of the aims of the Moray Economic Strategy.
A broad business base with stable, well paid employment; a focus on high quality jobs in engineering; science and technology; growth of established tourism, food, drink sectors. | LDP supports this aim by identifying employment land designations to support the requirements identified in the Moray Economic Strategy.
LDP supports this aim through the Primary Policy PP1 Sustainable Economic Growth which supports proposals that assist in the delivery of the aims of the Moray Economic Strategy.
LDP supports this aim by including a suite of Economic Development policies which help create conditions which support economic growth, sustain and create jobs and contribute to the well being and prosperity of the area.
Sufficient housing land to meet the Housing Need and Demand Assessment (HNDA), that will facilitate the provision of affordable housing, and to ensure high quality residential developments | LDP supports this aim by identifying housing land designations to meet strategic housing land requirements for 2013 to 2025 and ensure a five year effective housing land supply at all times. Over provision of HNDA requirements to provide flexibility.
LDP supports this aim by containing policies to require new housing developments of four or more houses to provide a minimum of 25% of the total units as affordable housing.
LDP supports this aim through Primary Policy PP3 Placemaking and supporting supplementary guidance which aims to encourage higher standards of urban design.
Attractive, sustainable environments where people will wish to live and work, which incorporate high quality design; green corridors and open spaces. | LDP supports this aim through Primary Policy PP2 Climate Change and supporting supplementary guidance which amongst other things aims to encourage development in sustainable locations and the creation of quality open spaces, landscaped areas and green wedges.
LDP supports this aim through Primary Policy PP3 Placemaking and supporting supplementary guidance which aims to encourage higher standards of urban design.
LDP supports this aim through Policy E5: Open Spaces which safeguards open spaces, and sets out the quantative and qualitative requirements for new open space in development.
A policy context which supports growth and development, whilst at the same time protecting and enhancing the natural and built heritage, which are amongst Moray’s prime assets. | LDP supports this aim through the Primary Policy PP1 Sustainable Economic Growth which supports proposals that assist in the delivery of the aims of the Moray Economic Strategy where the quality of the natural and built environment is safeguarded.
LDP supports this aim through a chapter of policies relating to Environmental Resources. These contain policies to protect and safeguard the natural environment and built heritage. Other policies seek to protect the environment from activity that could have an adverse impact.
Good, efficient transport links to the rest of the country; with the encouragement of active travel as an alternative to journeys by car. | LDP support this aim through a suite of policies relating to Transportation and Accessibility which includes policies to promote the improvement of road, rail, air and sea routes in Moray and policies that aim to reduce travel demands and encourage active travel.
Renewable energy technologies; reduced carbon emissions; embedded within all development | LDP supports this aim through Primary Policy PP2 Climate Change and supporting supplementary guidance which requires proposals to reduce green house gas emissions including utilising sustainable construction techniques, and installing low and zero carbon generating technologies.
LDP supports this aim through Policy ER1: Renewable Energy Proposals and ER2 Carbon Emission Reduction and associated Technical Guidance Note.

## Policies
KEY |  | Sites/Actions in danger of non delivery | C | Action complet
|  | Sites/Actions where there is little happening but no specific risk to non-development | O | Action on-going
Sites/Actions being actively progressed
2. Policy Actions
Action Ref. | Policy Group | Policy | Actions | Responsible/ Lead | Other Partners | Timescale | Progress
P1 | All Policies | All Policies | Take planning decisions in line with policy. | MC Dev Mgt | MC Dev Plans, Local Review Body | Ongoing | Applications are determined in accordance with the Local Development Plan 2015 unless material considerations indicate otherwise . | O
P2 | All Policies | All Policies | Development Management Training on key policy changes. | MC Dev Plans | MC Dev Mgt | Prior to adoption | Training with Development Management was undertaken on the key Policy changes. Training was provided on PP3 Placemaking, H7 Housing in the Open Countryside, E5 Open Spaces, PP2 Climate Change and ER2 Development in Woodlands. This included guidance on the requirement for compensatory planting. From the training day it was established that a Policy Log would help with the interpretation of the new policies. The Policy Log has now been set up. Separate training sessions were held with Forestry Commission in respect of compensatory planting and with SNH on natura issues. | C
P3 | All Policies | All Policies | Identify key monitoring indicators for the policies within the plan, supplementary guidance and SEA indicators. | MC Dev Plans | MC Dev Mgt | Prior to adoption | Annual monitoring of the Local Development Plan will be reported to Committee. | C
P4 | All Policies | All Policies | Set up and implement monitoring of key indicators. | MC Dev Plans | MC Dev Mgt | On adoption of plan | An annual report on LRB statistics and trends will be prepared and reported to the Planning and Regulatory Services Committee as part of the Moray Local Development Plan Monitoring Report. Monitoring of the Quality Audit is being undertaken to assess the implementation of PP3 Placemaking and will inform any changes to policy in the next MLDP. | C
P5 | Primary Policies | PP1 | Various actions are contained within the Moray Economic Strategy, these include industrial estate remodelling, signature visitor facilities, serviced residential accommodation, regional sports facilities and a new arts school/centre. The actions of the Moray Economic Strategy will be taken forward by one of it's Theme Groups which is accountable to the Moray Economic Partnership and Moray Community Planning Partnership. Further details are contained within the Moray Economic Strategy Action Plan. | See Moray Economic Strategy Action Plan |  |  | A refresh of the Moray Economic Strategy is being carried out this financial year 2017/2018 and will include an update on Actions.
P6 | Primary Policies | PP2 | Preparation and consultation on Climate Change Supplementary Guidance. | MC Dev Plans |  | Consultation in tandem with Proposed Plan. Adoption alongside Local Development Plan. | Climate Change Supplementary Guidance was adopted alongside the Local Development Plan. Efforts have been made to make developers aware of the new policy and the requirement to submit a sustainability statement for development of 10 or more houses. | C
P7 | Primary Policies | PP3 | Consultation on Placemaking- Urban Design Guide Supplementary Guidance. | MC Dev Plans |  | Consultation in tandem with Proposed Plan. Adoption alongside Local Development Plan. | The Urban Design Supplementary Guidance was adopted alongside the Local Development Plan in 2015. | C
P8 | Primary Policies | PP3 | Actively engage at an early stage with developers to raise standards of design. Prioritising those sites where the need for masterplans or development briefs are identified in settlement designations. For all other sites encourage discussion with developers early in process. Use information gathered in bid checklists as basis for initial discussions. | MC Dev Plans | Developers | Ongoing | The Development Plans section has actively engaged with developers at an early pre-application stage to raise awareness of the new MLDP policies. Early engagement took place on two major residential masterplans/planning applications in Elgin and one in Forres to raise design standards and ensure compliance with PP3 Placemaking. The section has also been proactive in contacting developers/landowners regarding the new Placemaking Policies and has encouraged early dialogue over any sites that may be brought forward. A series of development briefs are currently being prepared on several key sites which will be reported to the Planning and Regulatory Services Committee at the end of the year. | O
P9 | Primary Policies | PP3 | Encourage early discussion for all development and promote submission of design statements for all development over 10 houses. | MC Dev Plans | MC Dev Mgt | Ongoing | Developers were invited to a training/awareness day that provided information and guidance on the Policy requirements of PP3. This included the requirement of a design statement for development proposals of 10 or more houses. Active engagement has also been undertaken with developers regarding the introduction of the Quality Audit which will accompany a Design Statement for proposals of 10 or more houses. | O
P10 | Primary Policies | PP3 | Encourage developers to complete quality audits to be assessed by officers from MC Dev Plan, MC Dev Mgt, MC Transportation and MC Housing | Developers | MC Dev Plans, MC Dev Mgt, MC Transportation, MC Housing | Ongoing | To date 12 quality audits have been completed. Anaylsis of the completed audits shows that they have been successful in applying consistency to the Placemaking policy and achieving design improvements. | O
P11 | Primary Policies | PP3 | Quality Audit Monitoring | MC Dev Plans | MC Dev Mgt, MC Transportation, MC Housing | Ongoing | Monitoring of the Quality Audit is being undertaken to assess the implementation of PP3 Placemaking and will help to inform any changes to the policy in the next MLDP. | O
P11 | Economic Development and Employment Land | Policy ED1 Development of New Employment Land, Policy ED2 Business Uses on Industrial Estates Policy ED3 Business Parks, Policy ED7 Rural Business Proposals | Preparation of Employment Land Audit to monitor take up and supply of employment land. | MC Dev Plans | Developers, HIE | Annually | The Employment Land Audit for 2017 was presented to the Planning and regulatory Services Committee on 30 May. This highlighted the limited supply of marketable/effective supply of employment land in Elgin and the shortage of serviced land for immediate development across Moray. | C
P12 | Economic Development and Employment Land | Policy ED5 Opportunity Sites | Monitor through Employment Land Audit. | MC Dev Plans | Developers, HIE | Annually | The Employment Land Audit for 2017 was presented to the May 30 Planning and Regulatory Services Committee. More detailed comments are provided on progress of individual sites within the Settlement section of this Action Programme. | C
P13 | Economic Development and Employment Land | Policy ED6 Digital Communications | Work with Arqiva to implement mobile infrastructure improvements. | MC Dev Plans | MC Dev Mgt | Operating by 2015 | The programme of improvement was not progressed by Arqiva
P14 | Residential Development | Policy H1 Housing Land, Policy H2 Long Term Housing Designations (LONG) | Preparation of Housing Land Audit to monitor housing supply and ensure five year effective supply is maintained. Supplementary or other guidance will be prepared to address the detailed implementation and approach to LONG sites and the conditions which will apply to early/partial releaser and/or progression through the next local development plan. | MC Dev Plans | Developers | Annually | Housing Land Audit for 2017 has been completed and approved by Planning & Regulatory Services Committee on 30 May. The Housing Land Audit 2017 shows an effective housing land supply of 4094 units, meeting the requirements to have a five year effective supply. Completions have decreased from 337 in 2015 to 334 in 2016. However this is lower than the HNDA 2012 target figure of 538 units per annum. While the overall effective land supply is good, the projected house completions reflect the low supply of new housing in Keith and Speyside. Officers are currently looking at how existing sites can be made more effective as part of the preparation for the MLDP 2020. | C
P15 | Residential Development | Policy H5 Development within Rural Groupings | Supplementary Guidance on rural groupings will be produced alongside the LDP. However, early review of this will be undertaken post adoption of the LDP. | MC Dev Plans | MC Dev Mgt, MC Trans, other Council Services, Scottish Water, SEPA, SNH | Review of Supplementary Guidance post LDP adoption with revised SG in place two years post adoption. | A review of the rural grouping supplementary guidance has been undertaken and was adopted in June 2016. The new guidance proposes a modest number of new development opportunities to existing rural groupings. As part of the review landscape expertise was commissioned to assist in addressing identified build up issues. This provides scope for a further review to identify a significant number of new rural groupings and inform a future housing in the countryside policy review that will be considered through the Main Issues Report as part of the preparation of the next Local Development Plan. | C
P16 | Residential Development | Policy H6 Re-use and Replacement of Existing Buildings in the Countryside, Policy H7 New Housing in the Open Countryside | Preparation and consultation on revised Housing in the Countryside Supplementary Guidance. | MC Dev Plans |  | Consultation in tandem with Proposed Plan. Adoption alongside Local Development Plan. | The revised Housing in the Countryside Supplementary Guidance was adopted alongside the Local Development Plan. The review of rural groupings identified a significant number of areas of countryside that are under pressure from development. The review highlighted that rural groupings are not functioning as intended with a low take up of development on designated sites. There is a clear relationship between rural groupings and housing in the countryside and the next Housing in the Countryside Policy should seek to address the balance and assist in promoting development in rural groupings. This will be considered through the Main Issues Report as part of the preparation of the next Local Development Plan. | C
P17 | Residential Development | H8 Affordable Housing | Preparation and consultation on Affordable Housing Supplementary Guidance. | MC Dev Plans |  | Consultation in tandem with Proposed Plan. Adoption alongside Local Development Plan. | The Affordable Housing Supplementary Guidance was adopted alongside the plan. An awareness day was held with developers to provide information on the change of policy. | C
P18 | Residential Development | H8 Affordable Housing | Joint working with Housing Service in respect of delivery of affordable housing. | MC Dev Plans, MC Housing, MC Dev Mgt |  | Ongoing | On-going joint working with the Housing Service in delivering affordable housing. The Housing Service take part in the Quality Audit process to ensure that compliance with H8 and to ensure that housing is well integrated. The Housing Service have been involved in the preparation of both Findrassie and Elgin South Masterplans, with affordable housing being delivered in both first phases of each masterplan. Affordable Housing is delivered through planning conditions and S.75 legal agreements. | O
P19 | Residential Development | Policy H9 Housing Mix/Accessible Housing | Preparation and consultation on Accessible Housing Supplementary Guidance. | MC Dev Plans, MC Housing |  | Consultation in tandem with Proposed Plan. Adoption alongside Local Development Plan. | Supplementary Guidance was adopted with the plan. A revised version of the Supplementary Guidance was adopted on 6 September 2016 which requires half (50%) of the private sector accessible housing units that are delivered are single storey i.e. a bungalow to ensure a mix of house types that more accurately reflects need and demand. | C
P20 | Environmental Resources - Natural Environment | Policy E4 Trees and Development | Preparation and consultation on Supplementary Guidance in respect of High Hedges. | MC Dev Mgt |  | Supplementary Guidance in place two years post adoption. | Guidance is available on The Moray Council website in respect of High Hedges and training for Members was undertaken. Reference to High Hedges should be removed from the Justification of Policy E4 in the next LDP as it does not relate to Policy E4 Trees and Devlopment and is not under the Planning Acts . | C
P21 | Environmental Resources - Natural Environment | Policy E4 Trees and Development | Preparation and consultation on Trees and Development Supplementary Guidance. | MC Dev Plans |  | Consultation in tandem with Proposed Plan. Adoption alongside Local Development Plan. | Guidance adopted alongside Local Development Plan. Development Management training day provided further information on compensatory planting. | C
P22 | Environmental Resources - Natural Environment, Environmental Resources | Policy E4 Trees and Development, Policy ER3 Development in Woodlands | Identify any new Tree Preservation Order candidates. | MC Dev Plans | MC Legal | Ongoing | A survey of all of the Tree Preservation Orders (TPO's) has been undertaken since the adoption of the Local Development Plan. As a result of the review 3 new TPO's have been served, 2 revoked, and 1 modified. Sites have been identified for compensatory planting. | C
P23 | Environmental Resources - Natural Environment | Policy E5 Open Space | Preparation and consultation on Open Space Strategy. | MC Dev Plans | MC Dev Mgt, MC Trans, MC Education, other Council Services, Scottish Water, SEPA, SNH | Supplementary Guidance in place two years post adoption. | The Open Space Strategy has been completed and been through public consultation. It will be presented to the the Planning and Regulatory Services Committee for approval on 15 August 2017. It provides a strategic vision for the provision, development, maintenance and management of open space and the application of standards aims to improve consistency in decision making and will support the provide guidance in respect of MLDP Policy E5 Open Spaces. If approved, it will be adopted as statutory Supplementary Guidance. | C
P24 | Environmental Resources - Built Environment | Policy BE2: Listed Buildings, Policy BE3: Conservation Area | Townscape Heritage Improvements are an action of the Moray Economic Strategy and action will be taken forward by one of it's Theme Groups which is accountable to the Moray Economic Partnership and Moray Community Planning Partnership. Further details of this action are contained within the Moray Economic Strategy Action Plan. | See Moray Economic Strategy Action Plan |  |  | A refresh of the Moray Economic Strategy is being carried out this financial year 2017/2018 and will include an update on Actions.
P25 | Environmental Resources - Built Environment | Policy BE3: Conservation Area | Preparation and consultation on Conservation Area Appraisals. | MC Dev Plans |  | Ongoing | Conservation Area Appraisals have been completed for Findhorn and Cullen. Guidance on Windows and Doors has also been completed and approved. A review of Moray's Conservation Areas is being undertaken as part of the preparation for the next Local Development Plan. | C
P26 | Environmental Resources- Environmental Protection | Policy EP5: Surface Water Drainage | Preparation and consultation of supplementary guidance on surface water drainage and flooding. | MC Flood | MC Dev Plans | Within a year of adoption. | There has been a delay in progressing this SG due to lack of available resources. It will be progressed when resources are available.
P27 | Environmental Resources - Environmental Resources | Policy ER1 Renewable Energy Proposals | Moray Landscape Capacity Study and Moray Onshore Wind Energy Supplementary Guidance. Further detail on the above assessment process will be addressed through supplementary guidance to include: peat mapping once this becomes available, detailed mapping of constraints, guidance on areas with greatest potential for small/medium and large scale windfarms. | MC Dev Plans |  | Carry forward with adoption as Supplementary Guidance on adoption of the plan. | Updates to the Moray Landscape Capacity Study and Moray Onshore Wind Energy Guidance have been completed in alignment with Scottish Planning Policy. The documents were approved at a meeting of the Planning and Regulatory Services Committee on 28 February 2017. The finalised documents have been sent to the Scottish Government for approval where they will become statutory Supplementary Guidance. | O
P28 | Environmental Resources - Environmental Resources | Policy ER5 - Minerals | Monitor mineral consents and reserves to ensure land bank of construction aggregates. | MC Dev Plans | Minerals Association and quarry operators | Annually | On going monitoring being undertaken. A revised minerals audit to be undertaken in 2017/18 as part of evidence base for LDP.
P29 | Transportation | Policy T1 Transport Infrastructure Improvements | Promote priority improvements identified in Policy. | MC Trans, HiTrans | MC Dev Plans, Scottish Gov't | Ongoing | A new Transport Strategy for Elgin has been prepared and undergone public consultation. It is anticipated that ths will be presented to Full Council in August 2017. See Action EI25 in respect of A96 dualling.
P30 | Transportation | Policy T1 Transport Infrastructure Improvements | Improved Regional Public Transport Links are an action of the Moray Economic Strategy and action will be taken forward by one of it's Theme Groups which is accountable to the Moray Economic Partnership and Moray Community Planning Partnership. Further details of this action are contained within the Moray Economic Strategy Action Plan. | See Moray Economic Strategy Action Plan |  |  | A refresh of the Moray Economic Strategy is being carried out this financial year 2017/2018 and will include an update on Actions.
P31 | Transportation | Policy T4 Safeguarding Bus, Rail, and Harbour Facilities | Buckie Quayside Provision is an action of the Moray Economic Strategy and action will be taken forward by one of it's Theme Groups which is accountable to the Moray Economic Partnership and Moray Community Planning Partnership. Further details of this action are contained within the Moray Economic Strategy Action Plan. | See Moray Economic Strategy Action Plan |  |  | A refresh of the Moray Economic Strategy is being carried out this financial year 2017/2018 and will include an update on Actions.
P32 | Transportation | Policy T5 Parking Standards | Keep Parking Standards under review and update if necessary. | MC Trans, MC Dev Plans |  | Ongoing | A parking strategy for Elgin has been undertaken and it is anticipated that it will be presented to committee later in the year. Supplementary Guidance on parking standards is currently being prepared by Transportation in alignment with the Main Issues Report timescale.
P33 | Transportation | Policy T7 Safeguarding and promotion of walking, cycling and equestrian networks | Promote provision of and improvements through policy and developer obligations. | MC Dev Plans , Moray Council Access Manager |  | Ongoing | The Council has been active in promoting the improvement of walking, cycling, and equestrian networks within new developments across Moray. Providing the necessary infrastructure to promote walking and cycling has been at the heart of the recently prepared Findrassie and Elgin South Masterplans. The Quality Audit process and implementation of PP3 Placemaking has improved walking and cycling networks on other recent major residential developments. An Active Travel Strategy for Moray has been prepared by the Transportation section. | O
P34 | Transportation | Policy T7 Safeguarding and promotion of walking, cycling and equestrian networks | Development and promotion of linking infrastructure is an action of the Moray Economic Strategy and action will be taken forward by one of it's Theme Groups which is accountable to the Moray Economic Partnership and Moray Community Planning Partnership. Further details of this action are contained within the Moray Economic Strategy Action Plan. | See Moray Economic Strategy Action Plan |  |  | A refresh of the Moray Economic Strategy is being carried out this financial year 2017/2018 and will include an update on Actions.
P35 | Retail and Commercial Development | Policy R1 Town Centre Development | Completion of Town centre Health Checks | MC Dev Plans |  | Every two years | Town Centre healthchecks are prepared biannually. A healthcheck was completed in 2016 with the next one being prepared for 2018.
P36 | Retail and Commercial Development | Policy R1 Town Centre Development | Central area site enabling is action of the Moray Economic Strategy and action will be taken forward by one of it's Theme Groups which is accountable to the Moray Economic Partnership and Moray Community Planning Partnership. Further details of this action are contained within the Moray Economic Strategy Action Plan. | See Moray Economic Strategy Action Plan |  |  | A refresh of the Moray Economic Strategy is being carried out this financial year 2017/2018 and will include an update on Actions.
P37 | Implementation | IMP3 Developer Obligations | Prepare and consult on Developer Obligations Supplementary Guidance. | MC Dev Plans | Planning Gain Unit | Supplementary Guidance in place two years post adoption. | Supplementary Guidance was approved by the Scottish Government on 14 October 2016 and now forms part of the statutory Moray Local Development Plan. This is currently under review and will be presented to Committee in August 2017. | C
P38 | Implementation | IMP3 Developer Obligations | Creation of Infrastructure Delivery Group and implementation of IMP3 and Developer Obligations SG. | MC Dev Plans | Community Planning Partners and Infrastructure Providers | Ongoing | Preparation of the Developer Obligations Supplementary Guidance has identified the need for longer term co-ordinated planning for infrastructure between community planning partners and infrastructure providers. An Infrastructure Delivery Group (IDG) has been set up to proactively co-ordinate the planning and delivery of infrastructure in Moray. The IDG is led by Development Planning and Facilitation and includes representatives from the Council’s Transportation Service, Education Service, Development Management, NHS Grampian and Scottish Water. Representatives from other Council Services and infrastructure providers are invited to attend when required. This group also ensures that there is a strong evidence base for which to seek developer obligations to avoid legal challenges and monitors the delivery of infrastructure. | O
P39 | Implementation | IMP3 Developer Obligations | Infrastructure Plan for Elgin, Forres and Buckie | MC Dev Plans | Community Planning Partners and Infrastructure Providers | Ongoing | Preparation of future infrastructure plans for Moray's main towns to be produced for the next Main Issues Report due to be reported to Committee in December 2017. | O
P40 | SEA | SEA | Enhance bid checklist template to more directly relate to SEA (See action P8 regarding ongoing use of checklists). | MC Dev Plans |  | Prior to LDP adoption | A revised bid checklist has been produced that includes elements that directly relates to SEA. The checklist is currently being used to assess bids in preparation for the next local development plan. | C
P41 | Environmental Resources | ER2 Development in Woodlands | Preparation of a Woodland Strategy | MC Dev Plans | SNH, HIE, and the Forestry Commission | Supplementary Guidance in place early 2017 | A Woodlands Strategy has been prepared to inform the development of forestry and woodland in Moray. The finalised document will be presented to Committee in August 2017 | C
P42 | Transportation | Policy T1 Transport Infrastructure Improvements | Forres Integrated Transport Plan | MC Trans, MC Dev Plans |  |  | To inform the Main Issues Report to be reported to Committee in December 2017. | O
P43 | Environmental Protection | EP7 Control of Development in Flood Risk Areas and other relevant EP policies. | Strategic Flood Risk Assessment | Moray Flood Alleviation Team |  | Ongoing | The team are preparing a Strategic Flood Risk Assesment (SFRA) to support the Main Issues Report in preparation of the MLDP 2020. The SFRA will be used to inform choices about the location of development and policies for flood risk management. | O

## Essential Infrastructure
3. Essential Settlement Infrastructure
Action Reference | Settlements | Constraint/Issues | Action | Timescale | Progress
EI1 | All developments in Aberlour, Archiestown, Craigellachie, Fochabers, Garmouth, Kingston, Lhanbryde, Mosstodloch, Portgordon, Rothes, Urquhart | Badentinan WTW serves several settlements where new development is proposed and therefore cumulative impacts of development on capacity will require to be considered. | Developers to engage with Scottish Water. Scottish Water will invest in asset infrastructure (subject to the 5 growth criteria being met) to ensure sufficient capacity is provided to meet development needs, subject to no adverse effect on the integrity of the River Spey SAC. | Ongoing | Currently sufficient capacity at Badentinan WTW. Developers are encouraged to engage early with Scottish Water through Scottish Water's pre-development enquiry form.
EI2 | All developments in Alves, Burghead, Cummingston, Dufftown, Dyke, Elgin, Forres, Findhorn, Hopeman, Kinloss, Lossiemouth | Glenlatterach and Badentinan WTW serves several settlements where new development is proposed and therefore the cumulative impacts of development on capacity will require to be considered. | Developers to engage with Scottish Water. Scottish Water will invest in asset infrastructure (subject to the 5 growth criteria being met) to ensure sufficient capacity is provided to meet development needs. | Ongoing | Capacity at Glenlatterach WTW has changed and Scottish Water are encouraging developers to contact them as early as possible through Scottish Water's pre-development enquiry form to discuss capacity/build out rates
EI3 | All developments in Buckie, Cullen, Findochty, Portknockie, Rothiemay | Turriff WTW serves several settlements where new development is proposed and therefore cumulative impacts of development on capacity will require to be considered. | Developers to engage with Scottish Water. Scottish Water will invest in asset infrastructure (subject to the 5 growth criteria being met) to ensure sufficient capacity is provided to meet development needs. | Ongoing | Currently sufficient capacity at Turriff WTW. Developers are encouraged to engage early with Scottish Water through Scottish Water's pre-development enquiry form.
EI4 | All developments in Dallas, Rafford | Glenlatterach WTW serves several settlements where new development is proposed and therefore cumulative impacts of development on capacity will require to be considered. | Developers to engage with Scottish Water. Scottish Water will invest in asset infrastructure (subject to the 5 growth criteria being met) to ensure sufficient capacity is provided to meet development needs. | Ongoing | Capacity at Glenlatterach WTW has changed and Scottish Water are encouraging developers to contact them as early as possible through Scottish Water's pre-development enquiry form to discuss capacity/build out rates
EI5 | All development in Keith, Newmill | There is capacity for 124 houses at Herricks WTW which supplies Keith. The cumulative impacts of development will require to be considered. | Developers to engage with Scottish Water. Scottish Water will invest in asset infrastructure (subject to the 5 growth criteria being met) to ensure sufficient capacity is provided to meet development needs. | Ongoing | Currently sufficient capacity at Herricks WTW. Developers are encouraged to engage early with Scottish Water through Scottish Water's pre-development enquiry form.
EI6 | All development in Alves, Burghead, Cummingston, Elgin, Hopeman, Lhanbryde, Lossiemouth, Urquhart | Moray West WWTW serves several settlements where new development is proposed and therefore the cumulative impacts of development on capacity will require to be considered. | Developers to engage with Scottish Water. Scottish Water will invest in asset infrastructure (subject to the 5 growth criteria being met) to ensure sufficient capacity is provided to meet development needs. | Ongoing | There is currently sufficient capacity at Moray West WWTW. Developers are encouraged to engage early with Scottish Water through Scottish Water's pre-development enquiry form.
EI7 | All developments in Buckie, Cullen, Findochty, Portgordon, Portknockie | Moray East WWTW serves several settlements where new development is proposed and therefore the cumulative impacts of development on capacity will require to be considered. | Developers to engage with Scottish Water. Scottish Water will invest in asset infrastructure (subject to the 5 growth criteria being met) to ensure sufficient capacity is provided to meet development needs. | Ongoing | There is currently sufficient capacity at Moray East WWTW. Developers are encouraged to engage early with Scottish Water through Scottish Water's pre-development enquiry form.
EI8 | All developments in Findhorn, Forres and Kinloss | Forres WWTW serves several settlements where new development is proposed and has limited capacity. Therefore the cumulative impacts of development on capacity will require to be considered. | Developers to engage with Scottish Water. Scottish Water will invest in asset infrastructure (subject to the 5 growth criteria being met) to ensure sufficient capacity is provided to meet development needs. | Ongoing | There is currently sufficient capacity at Forres WWTW. However, growth will be required should all the proposed development go ahead. Developers are encouraged to engage early with Scottish Water through Scottish Water's pre-development enquiry form.
EI9 | All developments in Fochabers, Mosstodloch | Fochabers WWTW serves several settlements where new development is proposed and has limited capacity (49 houses). Therefore the cumulative impacts of development on capacity will require to be considered. | Developers to engage with Scottish Water. Scottish Water will invest in asset infrastructure (subject to the 5 growth criteria being met) to ensure sufficient capacity is provided to meet development needs. | Ongoing | There is limited capacity at Focahbers WWTW. Developers are encouraged to contact Scottish Water as soon as possible through Scottish Water's pre-development enquiry form to discuss growth requirements and build out rates.
EI10 | All developments in Dufftown | Capacity for 21 houses atDufftown WWTW. Cumulative impacts of development on capacity will require to be considered. | Developers to engage with Scottish Water. Scottish Water will invest in asset infrastructure (subject to the 5 growth crietria being met) to ensure sufficient capacity is provided to meet development needs, subject to no adverse effect on the integrity of the River Spey SAC. | Ongoing | There is limited capacity at Dufftown WWTW. Developers are encouraged to engage early with Scottish Water through Scottish Water's pre-development enquiry form to discuss growth requirements and build out rates.
EI11 | All development in Aberlour | Capacity for 30 houses at Aberlour WWTW. Cumulative impacts of development will require to be considered. | Developers to engage with Scottish Water. Scottish Water will invest in asset infrastructure (subject to the 5 growth criteria being met) to ensure sufficient capacity is provided to meet development needs, subject to no adverse effect on the integrity of the River Spey SAC. | Ongoing | There is currently sufficient capacity at Aberlour WWTW. Developers are encouraged to engage early with Scottish Water through Scottish Water's pre-development enquiry form.
EI12 | All development in Archiestown | Capacity for 28 houses at Archiestown WWTW. Cumulative impacts of development will require to be considered. | Developers to engage with Scottish Water. Scottish Water will invest in asset infrastructure (subject to the 5 growth criteria being met) to ensure sufficient capacity is provided to meet development needs, subject to no adverse effect on the integrity of the River Spey SAC. | Ongoing | There is currently sufficient capacity at Archiestown WWTW. Scottish Water are encouraging developers to contact them as early as possible through Scottish Water's pre-development enquiry form.
EI13 | All development in Craigellachie | Capacity for less than 10 houses at Craigellachie WWTW. Cumulative impacts of development will require to be considered. | Developers to engage with Scottish Water. Scottish Water will invest in asset infrastructure to ensure sufficient capacity is provided to meet development needs, subject to no adverse effect on the integrity of the River Spey SAC. | Ongoing | There is limited capacity at Craigellachie WWTW. Developers are encouraged to engage early with Scottish Water through Scottish Water's pre-development enquiry form to discuss growth requirments and build out rates.
EI14 | All development in Dallas | Capacity for less than 10 houses at Dallas WWTW. Cumulative impacts of development will require to be considered. | Developers to engage with Scottish Water. Scottish Water will invest in asset infrastructure (subject to the 5 growth criteria being met) to ensure sufficient capacity is provided to meet development needs. | Ongoing | Developers are encouraged to contact Scottish Water as early on as possible to establish growth requirements and discuss build out rates.
EI15 | All development in Dyke | Capacity for 25 houses at Dyke WWTW, this is sufficient to meet development proposals. | Developers to engage with Scottish Water. Scottish Water will invest in asset infrastructure (subject to the 5 growth criteria being met) to ensure sufficient capacity is provided to meet development needs. | Ongoing | There is limited capacity at Dyke WWTW. Developers are encouraged to engage early with Scottish Water through Scottish Water's pre-development enquiry form.
EI16 | All development in Garmouth | There is capacity for less that 10 houses at Garmouth WWTW. | Developers to engage with Scottish Water. Scottish Water will invest in asset infrastructure (subject to the 5 growth criteria being met) to ensure sufficient capacity is provided to meet development needs, subject to no adverse effect on the integrity of the River Spey SAC. | Ongoing | Developers are encouraged to contact Scottish Water as early on as possible to establish growth requirements and discuss build out rates.
EI17 | All development in Keith, Newmill | There is capacity for 90 houses at Keith WWTW. The cumulative impacts of development will require to be considered. | Developers to engage with Scottish Water. Scottish Water will invest in asset infrastructure (subject to the 5 growth criteria being met) to ensure sufficient capacity is provided to meet development needs. | Ongoing | There is limited capacity at Keith WWTW. Developers are encouraged to engage early with Scottish Water through Scottish Water's pre-development enquiry form.
EI18 | All development in Rothes | Capacity for less than 10 houses at Rothes WWTW. Cumulative impacts of development will require to be considered. | Developers to engage with Scottish Water. Scottish Water will invest in asset infrastructure (subject to the 5 growth criteria being met) to ensure sufficient capacity is provided to meet development needs, subject to no adverse effect on the integrity of the River Spey SAC. | Ongoing | Developers are encouraged to contact Scottish Water as early on as possible to establish growth requirements and discuss build out rates.
EI19 | All development in Rothiemay | There is capacity for less than 10 houses at Rothiemay Anderson Dr WWTW | Moray Council to work with Scottish Water to establish what is needed for development proposals, subject to no adverse effect on the integrity of the River Spey SAC. | Ongoing | Developers are encouraged to contact Scottish Water as early on as possible to establish growth requirements and discuss build out rates.
EI20 | Elgin | Potential capacity issues at number of schools in Elgin | Developers to engage with Moray Council Education at early stage to discuss potential requirements. | Ongoing. Moray Council School Estates Review commenced in Summer 2013 | Proposals for new catchment areas in Elgin were approved on the 11 November 2015 and became effective from 5 January 2016. The establishment of a new primary school in south east Elgin was agreed in April 2016. The Elgin South Masterplan and the phase one application include a site for the Primary School. Consultation on rezoning Moray Secondary Schools has also been undertaken. A review of Forres Catchment areas is being undertaken in Autumn 2016.
EI21 | Aberlour, Buckie, Burghead, Craigellachie, Cullen, Dufftown, Elgin, Fochabers, Forres, Keith, Lossiemouth, Mosstodloch | A number of potential road improvements have been identified in association with the development of sites in these settlements. Shown as TSP's | Developers will be responsible for implementing road improvements necessary as a result of their development and must contact MC Transportation at an early stage. | Ongoing | Early engagement with MC Transportation is encouraged.
EI22 | Elgin, Forres, Buckie and Keith | Implementation of priorities in Active Travel Audits | Developers will be responsible for implementing actions as they relate to their sites. MC Transportation will work to deliver wider improvements and priorities in partnership with developers and other agencies. | Ongoing | An active travel strategy has been prepared and it is anticipate that it will be presented to committee later in the year.
EI23 | Elgin | Elgin Traffic Management Programme - key objective is "to provide a quicker, safer, and more reliable transport system in and around Elgin while accommodating future development." |  | Ongoing | A new Transport Strategy for Elgin has been prepared and undergone public consultation. It is anticipated this will be presented to Full Council for approval towards the end of 2017.
EI24 | Elgin | Western Link Road - Key project of the Elgin Traffic Management Programme. | Project being progressed by Moray Council Consultancy | Pre-application consultation undertaken Sept 2013 | In March 2016 the Council agreed to remove the budget for the Western Link Road from the Capital Plan. By implication it is considered that, as funding is not available to promote the project, the WLR scheme is no longer a strategic project for the Council. A new Transport Strategy for Elgin has been prepared and it is anticipated this will be presented to Full Council in towards the end of 2017.
EI25 | Moray Wide - A96 corridor | A96 Dualling Inverness to Aberdeen | Design and development work being progressed by Transport Scotland on behalf of Scottish Government. MC | Public consultation took place in November 2013 and May 2015. The second stage of public consultation took place in June 2017. | In June 2016, Transport Scotland appointed consultants to carry out route option assessment and thereafter detailed design work for dualling the 29-mile western section of the A96 between Auldearn and Fochabers. The next stage of development (Design Manual for Roads and Bridges (DMRB) Stage 2 route option development and assessment) is expected to take approximately 2 years to complete, at which point a Preferred Option will be identified. Public consultation on potential routes is currently being undertaken.

## Aberlour
4. Site/Settlement Actions
Aberlour
Cross Reference to Essential Infrastructure Actions : EI1 (WTW), EI11 (WWTW), EI21 (TSP's)
Settlement | Site Reference | Allocation | Constraint/Key Infrastructure | Actions | Responsible/ Lead | Other Partners | Timescale/ Progress
Aberlour | R1 | 30 houses | Planning consent | Submit application as per settlement text, including technical assessments required. | Developer | MC Dev Mgt. | Demolition of existing house on the site approved, opening access for site to be redeveloped.
Aberlour | R2 and LONG | 40 houses (+50 LONG) | Planning consent | Submit application as per settlement text, including technical assessments required. | Developer | MC Dev Mgt. | No proposals brought forward to date. A Development Brief has been prepared by the Development Plans team in preparation for any development interest. The finalised brief will be presented to the Planning and Regulatory Services Committee later in the year. Projected timescales for development are beyond the current plan period.
|  |  | Development Brief required | Prepare and publish Development Brief in consultation with landowner/developer, other Council Services, Key Agencies and other relevant consultees. | MC Dev Plans | Landowner/ Developer, MC Dev Mgt, MC Trans, other Council Services Scottish Water, SEPA, SNH
|  |  | Access | Third party land required for offsite road improvements. Negotiations to secure improvements. Junction improvements required to Allachie Drive and at Allachie Drive/Chapel Terrace. | Developer | Third party owner
|  |  | Programming | Release "LONG" if triggers are met. | MC Dev Plans
Aberlour | R3 | 12 houses | Planning consent | Submit application as per settlement text, including technical assessments required. | Developer | MC Dev Mgt. | Planning consent granted for 19 houses.
|  |  | New waste water connection to the sewer in the main road will be required. | Early discussion with Scottish Water. | Developer | Scottish Water
Aberlour | R4 | 100 houses and business | Planning consent | Submit application as per settlement text, including technical assessments required. | Developer | MC Dev Mgt. | No proposals brought forward to date. A Development Brief will be prepared during the programme of development briefs being carried out by the development plans team. Approval in principle of junction agreed with Transport Scotland
|  |  | Development Brief required | Prepare and publish Development Brief in consultation with landowner/developer, other Council Services, Key Agencies and other relevant consultees. | MC Dev Plans | Landowner/ Developer, MC Dev Mgt, MC Trans, other Council Services Scottish Water, SEPA, SNH
|  |  | Access | New junction onto the A95. Prepare designs for new junction and agree with Transport Scotland. | MC Trans, Developer | MC Dev Plans, Transport Scotland
Aberlour | OPP1 | Business/ residential uses | Planning consent | Submit application as per settlement text, including technical assessments required. | Developer | MC Dev Mgt. | Site currently in use as a storage area. No planning consent for alternative use to date.

## Alves-Archiestown
Alves
Cross Reference to Essential Infrastructure Actions : EI2 (WTW), EI6 (WWTW), EI25 (A96)
Settlement | Site Reference | Allocation | Constraint/Key Infrastructure | Actions | Responsible/ Lead | Other Partners | Timescale/Progress
Alves | LONG | LONG | Programming | Release "LONG" if triggers are met. | MC Dev Plans |  | No proposals brought forward to date. Site is beyond the current plan period. Site is owned by The Moray Council and is currently leased to Moray Estates for agricultural use.
|  |  | Masterplan required | Prepare framework for preparation of Masterplan in consultation with other Council services, Key Agencies and other relevant consultees. Engage with landowner/developer. | MC Dev Plans | Landowner/ Developer, MC Dev Mgt, MC Trans, MC Education, other Council Services, Scottish Water, SEPA, SNH
|  |  |  | Prepare and consult on masterplan. Continue dialogue and work collaboratively with Moray Council, Key Agencies, and other relevant consultees as masterplan evolves. | Moray Council as Landowner | MC Dev Plans, MC Dev Mgt, MC Trans, MC Education, other Council Services, Scottish Water, SEPA, SNH
Archiestown
Cross Reference to Essential Infrastructure Actions : EI1 (WTW), EI12 (WWTW)
Settlement | Site Reference | Allocation | Constraint/Key Infrastructure | Actions | Responsible/ Lead | Other Partners | Timescale/Progress
Archiestown | R1 | 15 houses | Planning consent | Submit application as per settlement text, including technical assessments required. | Developer | MC Dev Mgt | No proposals brought forward to date.
Archiestown | R2 | 4 houses | Planning consent | Submit application as per settlement text, including technical assessments required. | Developer | MC Dev Mgt | No proposals brought forward to date.
Archiestown | R3 | 6 houses | Planning consent | Submit application as per settlement text, including technical assessments required. | Developer | MC Dev Mgt | No proposals brought forward to date.
Archiestown | R4 | 10 houses | Planning consent | Submit application as per settlement text, including technical assessments required. | Developer | MC Dev Mgt | No proposals brought forward to date.

## Buckie
Buckie
Cross Reference to Essential Infrastructure Actions : EI3 (WTW), EI7 (WWTW), EI21 (TSP's), EI22 (Active Travel Audits)
Settlement | Site Reference | Allocation | Constraint/Key Infrastructure | Actions | Responsible/ Lead | Other Partners | Timescale/Progress
Buckie | R1 | 20 houses | N/A | Development has consent and is under construction. | Developer |  | Planning consent for 2 units (13/00418/APP and 14/02109/APP).
Buckie | R2 | 64 houses | N/A | Development has consent and is under construction. | Developer |  | Site under construction. Planning consent for 49 units. | C
Buckie | R3 | 5 houses | Planning consent | Submit planning application as per settlement text, including technical assessments required. | Developer | MC Dev Mgt | Planning consent for 14 units refused (15/0852/APP) due to the development proposal encroaching into ENV land.
Buckie | R4 | 30 houses | Planning consent | Submit planning application as per settlement text, including technical assessments required. | Developer | MC Dev Mgt | Planning consent granted for a series of individual units. No units are yet complete.
Buckie | R5 | 60 houses | Planning consent | Submit planning application as per settlement text, including technical assessments required. | Developer | MC Dev Mgt | No proposals brought forward to date. Development constrained by access into the site.
Buckie | R6 | 60 houses | Planning consent | Submit planning application as per settlement text, including technical assessments required. | Developer | MC Dev Mgt | No proposals brought forward to date. Development constrained by the programming of development in R5 which has to come before the development of R6.
Buckie | R7 | 149 houses | N/A | Development has consent and is under construction. | Developer |  | Planning consent granted for 133 units (10/01847/APP). 99 units are complete with a further 34 units due to be completed by 2018. | C
Buckie | R8 | 175 houses | N/A | Development has consent and is under construction. | Developer |  | Planning consent for 175 units (08/02040/FUL). | C
Buckie | R9 | 170 houses | Planning consent | Submit planning application as per settlement text, including technical assessments required. | Developer | MC Dev Mgt | No proposals brought forward to date. Transport assessment required to determine the impact on the road infrastructure from the development of the site along with sites R10 and BP1.
|  |  | Access | Integrated approach required in respect of road infrastructure to serve the three sites. Joint Transport Assessment required withR9, R10 and BP1. Early discussion with Moray Council Transportation. | Developer | MC Trans
Buckie | R10 | 115 houses | Planning consent | Submit planning application as per settlement text, including technical assessments required. | Developer | MC Dev Mgt | No proposals brought forward to date. Transport assessment required to determine the impact on the road infrastructure from the development of the site along with R9 and BP1. Advance planting is also required prior to an application for planning permission being submitted.
Buckie | R10 | 115 houses | Access | Integrated approach required in respect of road infrastructure to serve the three sites. Joint Transport Assessment required withR9, R10 and BP1. Early discussion with Moray Council Transportation. | Developer | MC Trans
|  |  | Advance planting | Planting required to establish context and setting for new development. Planting prior to applying for planning permission. Early discussion with MC Dev Plans to agree requirements. | Developer | MC Dev Plans, MC Dev Mgt
Buckie | R11 | 105 houses | Planning consent | Submit planning application as per settlement text, including technical assessments required. | Developer | MC Dev Mgt | Planning application (16/00620/APP) for 112 units approved in March 2017.
|  |  | Advance planting | Planting required to establish context and setting for new development. Planting prior to applying for planning permission. Early discussion with MC Dev Plans to agree requirements. | Developer | MC Dev Plans, MC Dev Mgt
Buckie | I3 | 18.7 ha | Planning consent | Submit planning application as per settlement text, including technical assessments required. | Developer | MC Dev Mgt | Planning application (16/01629/APP) for storage and garage approved. Planning application (17/00193/APP) for road infrastructure and advanced planting approved.
Buckie | I4 | 10 ha | Planning consent | Submit planning application as per settlement text, including technical assessments required. | Developer | MC Dev Mgt | Malting facility on the site. No further planning consent for development of the site.
Buckie | I5 | 1.4 ha | Planning consent | Submit planning application as per settlement text, including technical assessments required. | Developer | MC Dev Mgt | Confirmation is still pending from the developer on Buckie Harbour to be used as a contingent port for the Beatrice Offshore Wind Limited windfarm. Promotion of the harbour including quayside facilities is still ongoing, particularly to attract construction and commissioning and operation and maintenance phases for the Moray Offshore Renewables Limited (MORL) windfarm. MORL is still to secure a market price through the next bidding round of Contract for Difference. Announcement expected Quarter 1 of 2017.
|  |  | N/A | Promotion of site as a location for an Operations and Maintenance base to support offshore wind industry. | MC Dev Plans, MC Trans | HIE
|  |  | Buckie Quayside Provision | Buckie Quayside Provision is an action of the Moray Economic Strategy and action will be taken forward by one of it's Theme Groups which is accountable to the Moray Economic Partnership and Moray Community Planning Partnership. Further details of this action are contained within the Moray Economic Strategy Action Plan. | See Moray Economic Strategy action plan
Buckie | OPP1 | Several alternative uses | Planning consent | Submit planning application as per settlement text, including technical assessments required. | Developer | MC Dev Mgt | Planning consent for 40 units renewed in 2014 (13/01845/APP).
|  | Several alternative uses | Access | Access dependent on type of use proposed. Early discussion with MC Trans required. | Developer | MC Trans
Buckie | OPP2 | Uses compatible with residential character | Planning consent | Submit planning application as per settlement text, including technical assessments required. | Developer | MC Dev Mgt | No proposals brought forward to date. Current use as storage area for cardboard and plastic ongoing.
Buckie | OPP3 | Business or residential | Planning consent | Submit planning application as per settlement text, including technical assessments required. | Developer | MC Dev Mgt | No proposals brought forward to date.
Buckie | OPP4 | Business, storage, or residential | Planning consent | Submit planning application as per settlement text, including technical assessments required. | Developer | MC Dev Mgt | No proposals brought forward to date.
|  |  | Access | Access dependent on type of use proposed. Early discussion with MC Trans required. | Developer | MC Trans
Buckie | OPP5 | Various uses | Planning consent | Submit planning application as per settlement text, including technical assessments required. | Developer | MC Dev Mgt | No proposals brought forward to date. Site currently derelict shipyard. Site has previously been subject to residential development proposal containing 122 units.
|  |  | Access | Access dependent on type of use proposed. Early discussion with MC Trans required. | Developer | MC Trans
Buckie | OPP6 | Housing or low activity business/industrial | Planning consent | Submit planning application as per settlement text, including technical assessments required. | Developer | MC Dev Mgt | No planning consent to date.
|  |  | Access | Access dependent on type of use proposed. Early discussion with MC Trans required. | Developer | MC Trans
Buckie | BP1 | 6.48 ha | Access | Integrated approach required in respect of road infrastructure to serve the three sites. Joint Transport Assessment required withR9, R10 and BP1. Early discussion with Moray Council Transportation. | Developer | MC Trans | No proposals brought forward to date. Transport assessment required to determine the impact on the road infrastructure from the development of the site along with sites R9 and R10.
Buckie |  |  | East Moray Science and Business Campus | East Moray Science and Business campus is an action of the Moray Economic Strategy and action will be taken forward by one of it's Theme Groups which is accountable to the Moray Economic Partnership and Moray Community Planning Partnership. Further details of this action are contained within the Moray Economic Strategy Action Plan. | See Moray Economic Strategy action plan

## Burghead- Craigellachie
Burghead
Cross Reference to Essential Infrastructure Actions : EI2 (WTW), EI6 (WWTW), EI21 (TSP's)
Settlement | Site Reference | Allocation | Constraint/Key Infrastructure | Actions | Responsible/ Lead | Other Partners | Timescale/Progress
Burghead | R1 | Gap sites | Planning consent | Submit planning application as per settlement text, including technical assessments required. | Developer | MC Dev Mgt | Planning consent for 6 units in southern section of site. No planning consent for northern part of the site.
Burghead | R2 |  | N/A | Development has consent and is under construction. |  |  | Planning consent for 42 units in total. | C
Burghead | R3 |  | N/A | Development has consent and is under construction. |  |  | Development has been completed.
Burghead | R4 | 60 houses | Planning consent | Submit planning application as per settlement text, including technical assessments required. | Developer | MC Dev Mgt | No proposals brought forward to date. A development brief has been prepared for the site to guide future development. The MOD were consulted during the preparation of the development brief to establish any development constraints.
|  |  | Ministry of Defence | Consultation required with Defence Infrastructure Organisation Safeguarding Department to establish the extent to which the site can be developed. | Developer, MC Dev Mgt | MOD/DIO
Burghead | R5 |  | N/A | Development has consent and is under construction. |  |  | Development has been completed.
Burghead | OPP1 | Housing or small scale business activities | Planning consent | Submit planning application as per settlement text, including technical assessments required. | Developer | MC Dev Mgt | No proposals brought forward to date.
Burghead | T2 | Caravan park extension | Planning consent | Submit planning application as per settlement text, including technical assessments required. | Developer | MC Dev Mgt | No proposals brought forward to date.
Craigellachie
Cross Reference to Essential Infrastructure Actions : EI1(WTW), EI13 (WWTW), EI21 (TSP's)
Settlement | Site Reference | Allocation | Constraint/Key Infrastructure | Actions | Responsible/ Lead | Other Partners | Timescale/Progress
Craigellachie | R1 | 5 houses | Planning consent | Submit planning application as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt | No proposals brought forward to date. Planning officer currently working to identify landowner of site.
Craigellachie | R2 | 20 houses | Planning consent | Submit planning application as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt | No proposals brought forward to date.
Craigellachie | R3 | 5 houses | Planning consent | Submit planning application as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt | No proposals brought forward to date. Planning officer currently working to identify landowner of site.
Craigellachie | R4 | 12 houses | N/A | Consent granted for 12 houses. | Developer | MC Dev Mgt | Planning consent granted for 7 houses (16/01558/APP & 16/01559/APP).

## Cullen-Cummingston-Dallas
Cullen
Cross Reference to Essential Infrastructure Actions : EI3 (WTW), EI7 (WWTW), EI21 (TSP's)
Settlement | Site Reference | Allocation | Constraint/Key Infrastructure | Actions | Responsible/ Lead | Other Partners | Timescale/Progress
Cullen | R1 | 30 houses | Planning consent | Submit application as per settlement text, including technical assessments required. | Developer | MC Dev Mgt | Planning consent granted to develop 5 houses on the western edge of the site (outline application followed by individual house applications). No planning consent has been granted for the remainder of the site.
Cullen | R2 | 55 houses | Planning consent | Submit application as per settlement text, including technical assessments required. | Developer | MC Dev Mgt | No planning consent to date.
Cullen | I1 | Commercial and business use | Planning consent | Submit application as per settlement text, including technical assessments required. | Developer | MC Dev Mgt | Application for house refused to ensure that site remains for industrial/commercial use.
Cullen | OPP1 | Alternative uses compatible with neighbouring residential | Planning consent | Submit application as per settlement text, including technical assessments required. | Developer | MC Dev Mgt | Planning consent extended (14/00029/APP & 14/00030/APP) for conversion of building and demolition of store/garage and the erection of 2 houses.
Cummingston
Cross Reference to Essential Infrastructure Actions : EI2 (WTW), EI6 (WWTW)
Settlement | Site Reference | Allocation | Constraint/Key Infrastructure | Actions | Responsible/ Lead | Other Partners | Timescale/Progress
Cummingston | R1 | 4 houses | Planning consent | Submit planning application as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt | Planning consent for 4 houses on the site. 1 house completed. | C
Dallas
Cross Reference to Essential Infrastructure Actions : EI4 (WTW), EI14 (WWTW)
Settlement | Site Reference | Allocation | Constraint/Key Infrastructure | Actions | Responsible/ Lead | Other Partners | Timescale/Progress
Dallas | R1 | 6 houses | Planning consent | Submit planning application as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt | No proposals brought forward to date.
|  |  | Drainage problems | Investigate and cost potential solution. | Developer
Dallas | R2 | 1 house | Planning consent | Submit planning application as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt | No proposals brought forward to date.
Dallas | R3 | 4 houses |  | Submit planning application as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt | Planning consent granted for 4 houses in May 2010. No development has taken place on the site.

## Dufftown-Dyke
Dufftown
Cross Reference to Essential Infrastructure Actions : EI2 (WTW), EI10 (WWTW), EI21 (TSP's)
Settlement | Site Reference | Allocation | Constraint/Key Infrastructure | Actions | Responsible/ Lead | Other Partners | Timescale/Progress
Dufftown | R1 | 36 houses | N/A | Planning consent in place and under construction. |  |  | Planning consent for 16 units granted in 2006. 9 units completed, further 7 units projected for completion by 2019. | C
Dufftown | R2 | 30 houses | Planning consent | Submit planning application as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt. | No proposals brought forward to date. Developer was required to demonstrate satisfactoy access could be achieved prior to inclusion within MLDP 2015.
Dufftown | R3 | 100 houses | Planning consent | Submit planning application as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt. | No proposals brought forward to date. Development brief programme currently being undertaken by development plans officers.
|  |  | Development Brief required | Prepare and publish Development Brief in consultation with landowner/developer, other Council Services, Key Agencies and other relevant consultees. | MC Dev Plans | Landowner/ Developer, MC Dev Mgt, MC Trans, other Council, Services Scottish Water, SEPA, SNH
Dufftown | R4 | 5 houses | Planning consent | Submit planning application as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt. | No proposals brought forward to date.
Dufftown | OPP1 | Business or residential | Planning consent | Submit planning application as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt. | Planning consent for 24 residential units. Development complete. | C
Dufftown | OPP2 | Residential, max two | Planning consent | Submit planning application as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt. | Planning consent granted for 2 residential units in 2010. No development has taken place on site.
Dufftown | OPP3 | Uses compatible with residential area | Planning consent | Submit planning application as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt. | No proposals brought forward to date. Business currently occupying the current premises on site.
Dyke
Cross Reference to Essential Infrastructure Actions : EI2 (WTW), EI15 (WWTW)
Settlement | Site Reference | Allocation | Constraint/Key Infrastructure | Actions | Responsible/ Lead | Other Partners | Timescale/Progress
Dyke | R1 | 12 houses | Planning consent | Submit planning application as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt | Application for planning permission in principle (15/01909/PPP) for 12 houses approved.
|  |  | Access | Number of units using junction of Darklass Road /Main Brodie to Dyke Road will require to be monitored. | MC Trans
Dyke | R2 | 5 houses | Planning consent | Submit planning application as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt | No proposals brought forward to date.
|  |  | Access | Number of units using junction of Darklass Road /Main Brodie to Dyke Road will require to be monitored. | MC Trans

## Elgin
Elgin
Cross Reference to Essential Infrastructure Actions : EI2 (WTW), EI6 (WWTW), EI20 (School Capacity), EI21 (TSP's) EI22 (Active Travel Audit), EI23 and EI24 (Elgin Traffic Management), EI25 (A96)
Settlement | Site Reference | Allocation | Constraint/Key Infrastructure | Actions | Responsible/ Lead | Other Partners | Timescale/Progress
Elgin | R1 | 20 houses | Programming/Access | Site constrained until delivery of TSP 3, 21,22, 23 and 24. | MC Consultancy |  | Access issues relating to the Western Link Road remain unresolved with the Moray Council deciding on 30 March 2016 not to fund the road construction.
Elgin | R2 | 395 houses | N/A | Consent granted and under construction. |  |  | 296 units built. Barratt currently constructing remaining housing under consent 08/02031/FUL and Springfield constructing flatted development of 16 units 14/00766/APP on the north west corner of the site. | C
Elgin | R3 | 75 houses | Planning Consent | Submit planning application as per settlement text and taking into account design principles, including any technical assessments required. | Developer | MC Dev Mgt | Access issues relating to the Western Link Road remain unresolved with the Moray Council deciding on 30 March 2016 not to fund the road construction. The Council are working in partnership with Scotia Homes and Grampian Housing Association on a masterplan for Bilbohall.
|  |  | Programming/Access | Site constrained until delivery of TSP 3, 21,22, 23 and 24. | MC Consultancy
|  |  | Development Brief required | Prepare and publish Development Brief in consultation with landowner/developer, other Council Services, Key Agencies and other relevant consultees. | MC Dev Plans | Landowner/ Developer, MC Dev Mgt, MC Trans, other Council, Services Scottish Water, SEPA
Elgin | R4 | 80 houses | Planning Consent | Submit planning application as per settlement text and taking into account design principles, including any technical assessments required. | Developer | MC Dev Mgt | Access issues relating to the Western Link Road remain unresolved with the Moray Council deciding on 30 March 2016 not to fund the road construction. The Council are working in partnership with Scotia Homes and Grampian Housing Association on a masterplan for Bilbohall.
|  |  | Programming/Access | Site constrained until delivery of TSP 3, 21,22, 23 and 24. | MC Consultancy
|  |  | Joint masterplan (R4 and R12) required | Prepare framework for preparation of Masterplan in consultation with other Council services, Key Agencies and other relevant consultees. Engage with landowner/developer. | MC Dev Plans | Landowner/ Developer, MC Dev Mgt, MC Trans, MC Education, other Council Services, Scottish Water, SEPA
|  |  |  | Prepare and consult on masterplan. Continue dialogue and work collaboratively with Moray Council, Key Agencies, and other relevant consultees as masterplan evolves. | Landowner/ Developer | MC Dev Plans, MC Dev Mgt, MC Trans, MC Education, other Council Services, Scottish Water, SEPA
Elgin | R5 | 435 houses | N/A | Consent granted and under construction. |  |  | Site being developed by Robertson Homes and Scotia Homes Ltd. 126 units are complete and both developers continue to be building on the site. The pylon line crossing the site has recently been undergrounded. | C
Elgin | R6 | 20 houses | Planning Consent | Submit planning application as per settlement text and taking into account design principles, including any technical assessments required. | Developer | MC Dev Mgt | Access issues relating to the Western Link Road remain unresolved with the Moray Council deciding on 30 March 2016 not to fund the road construction.
|  |  | Programming/Access | Site constrained until delivery of TSP 3, 21,22, 23 and 24. | MC Consultancy
Elgin | R7 and R8 | 200 houses | N/A | Consent granted and under construction. |  |  | Site currently being developed by Springfield Properties Plc and 116 homes are complete. Consent has been granted for an additional 19 houses on part of R8 that was realeased through the MLDP 2015. A planning application for 14 aparatments and 3 houses has been submitted for the part of R7 also released in MLDP 2015. | C
|  |  | Planning Consent | Submit planning application for remaining 20 as per settlement text and taking into account design principles, including any technical assessments required. | Developer | MC Dev Mgt
Elgin | R9 | 120 houses | Planning Consent | Submit planning application as per settlement text and taking into account design principles, including any technical assessments required. | Developer | MC Dev Mgt | Planning consent (15/02020/APP) for 132 houses approved.
Elgin | R10 | 85 houses | Planning Consent | Submit planning application as per settlement text and taking into account design principles, including any technical assessments required. | Developer | MC Dev Mgt | Application 15/02032/APP for 106 houses is under consideration and was approved at Committee in June 2016. Development on site is currently underway.
Elgin | R11 | 1500 houses | Planning Consent | Submit planning application as per settlement text and taking into account design principles, including any technical assessments required. | Developer | MC Dev Mgt | A masterplan has been prepared and adopted in December 2015 as Supplementary Guidance. The masterplan is a material consideration. Preparation of an action/implementation plan is to be prepared jointly by the Council and landowner. A Proposal of Application Notice for first phase planning application was submitted on 11 March 2016 for I8 and the south eastern part of R11. A application for planning permission in principle for the first phase was received on June 2017.
|  |  | Masterplan required. | Prepare framework for preparation of Masterplan in consultation with other Council services, Key Agencies and other relevant consultees. Engage with landowner/developer. | MC Dev Plans | Landowner/ Developer, MC Dev Mgt, MC Trans, MC Education, other Council Services, Scottish Water, SEPA, SNH
|  |  |  | Prepare and consult on masterplan. Continue dialogue and work collaboratively with Moray Council, Key Agencies, and other relevant consultees as masterplan evolves. | Landowner/ Developer | MC Dev Plans, MC Dev Mgt, MC Trans, MC Education, other Council Services, Scottish Water, SEPA, SNH
Elgin | R12 | 85 houses | Planning Consent | Submit planning application as per settlement text and taking into account design principles, including any technical assessments required. | Developer | MC Dev Mgt | Access issues relating to the Western Link Road remain unresolved with the Moray Council deciding on 30 March 2016 not to fund the road construction. The Council are working in partnership with Scotia Homes and Grampian Housing Association on a masterplan for Bilbohall.
|  |  | Masterplan required. | Prepare framework for preparation of Masterplan in consultation with other Council services, Key Agencies and other relevant consultees. Engage with landowner/developer. | MC Dev Plans | Landowner/ Developer, MC Dev Mgt, MC Trans, MC Education, other Council Services, Scottish Water, SEPA
|  |  |  | Prepare and consult on masterplan. Continue dialogue and work collaboratively with Moray Council, Key Agencies, and other relevant consultees as masterplan evolves. | Landowner/ Developer | MC Dev Plans, MC Dev Mgt, MC Trans, MC Education, other Council Services, Scottish Water, SEPA
Elgin | R13 | 20 houses | Planning Consent | Submit planning application as per settlement text and taking into account design principles, including any technical assessments required. | Developer | MC Dev Mgt | A development brief has been prepared for the site.
Elgin | R14 | 70 houses | Planning Consent | Submit planning application as per settlement text and taking into account design principles, including any technical assessments required. | Developer | MC Dev Mgt | No proposals brought forward to date.
Elgin | LONG 1 |  | Programming | Release "LONG" if triggers are met. | MC Dev Plans |  | Beyond plan period. Early discussion with landowner to consider the role of this site in the next Local Development Plan.
|  |  | Masterplan required. | Prepare framework for preparation of Masterplan in consultation with other Council services, Key Agencies and other relevant consultees. Engage with landowner/developer. | MC Dev Plans | Landowner/ Developer, MC Dev Mgt, MC Trans, MC Education, other Council Services, Scottish Water, SEPA, SNH
|  |  | Masterplan required. | Prepare and consult on masterplan. Continue dialogue and work collaboratively with Moray Council, Key Agencies, and other relevant consultees as masterplan evolves. | Landowner/ Developer | MC Dev Plans, MC Dev Mgt, MC Trans, MC Education, other Council Services, Scottish Water, SEPA, SNH
|  |  | Advance Planting | Advance planting of an avenue of trees along A941. | Developer
Elgin | LONG 2 |  | Programming | Release "LONG" if triggers are met. | MC Dev Plans |  | Masterplan for the LONG designation was approved for adoption as supplementray guidance in May 2017. Detailed planning application (16/01244/APP) for Phase 1 (870 houses, sports centre and sites for two primary schools) was approved at a pre-determination hearing in June 2017.
|  |  | Landscape Strategy | Prepare Landscape and Planting strategy for agreement with Council. Follow on action of planting. | Developer | MC Dev Plans
|  |  | Masterplan required. | Prepare framework for preparation of Masterplan in consultation with other Council services, Key Agencies and other relevant consultees. Engage with landowner/developer. | MC Dev Plans | Landowner/ Developer, MC Dev Mgt, MC Trans, MC Education, other Council Services, Scottish Water, SEPA, SNH
|  |  |  | Prepare and consult on masterplan. Continue dialogue and work collaboratively with Moray Council, Key Agencies, and other relevant consultees as masterplan evolves. | Landowner/ Developer | MC Dev Plans, MC Dev Mgt, MC Trans, MC Education, other Council Services, Scottish Water, SEPA, SNH
Elgin | I2 | 6.23 ha | Planning Consent | Submit planning application as per settlement text and taking into account design principles, including any technical assessments required. | Developer | MC Dev Mgt | It is undertsood that the remaining area is under offer and anticipate planning applications to be submitted soon.
Elgin | I6 | 4.5 ha | Planning Consent | Submit planning application as per settlement text and taking into account design principles, including any technical assessments required. | Developer | MC Dev Mgt | Private developer. Site serviced with road access. An application (Feb 2017) for a drive through coffee shop was approved in Feb 2017. An application (16/01883/APP) for a furniture shop is currently under consideration.
|  |  | Access | Link through to Linkwood Place required | Developer | MC Trans
Elgin | I7 | 30+ ha | Planning Consent | Submit planning application as per settlement text and taking into account design principles, including any technical assessments required. | Developer | MC Dev Mgt | With the development of the Barmuckity Strategic Development Framework the development is considered to be economically viable and deliverable within five years. This has meant that land at Barmuckity has moved from constrained to marketable/effective which has improved supply levels in Elgin, however further land will require to be identified in the next LDP to improve choice and enhance supply.
|  |  | N/A | Consent granted for road layout.
|  |  | Flood risk | A detailed flood risk assessment will be required along with detailed mitigation measures demonstrating the site can be developed. | Developer | SEPA
|  |  | Access strategy | Access strategy requires to be agreed with Transport Scotland for phase 2. | Developer | Transport Scotland
|  |  | Site promotion | Promotion of Barmuckity Business Park. This is an action of the Moray Economic Strategy and action will be taken forward by one of it's Theme Groups which is accountable to the Moray Economic Partnership and Moray Community Planning Partnership. Further details of this action are contained within the Moray Economic Strategy Action Plan. | See Moray Economic Strategy action plan
Elgin | I8 | 12 ha | Planning Consent | Submit planning application as per settlement text and taking into account design principles, including any technical assessments required. | Developer | MC Dev Mgt | Planning permission in principle application for the first phase of Findrassie. It does include this site but includes avenue planting along the site and access.
Elgin | BP/OPP | 4.12ha | Planning Consent | Submit planning application as per settlement text and taking into account design principles, including any technical assessments required. | Developer | MC Dev Mgt | Ongoing
|  |  | Monitor | Monitor development for business and other identified uses with a view to using information to inform future review of the site at the next Local Development Plan review. | Dev Plans
|  |  | Access | New access onto A96 required | Developer | MC Trans, Transport Scotland
|  |  | Elgin West Research and Innovation Park | Elgin West Research and Innovation Park is an action of the Moray Economic Strategy and action will be taken forward by one of it's Theme Groups which is accountable to the Moray Economic Partnership and Moray Community Planning Partnership. Further details of this action are contained within the Moray Economic Strategy Action Plan. | See Moray Economic Strategy action plan
Elgin | OPP1 | Industrial, business, office, distribution, retail | Planning Consent | Submit planning application as per settlement text and taking into account design principles, including any technical assessments required. | Developer | MC Dev Mgt | No proposals brought forward to date.
Elgin | OPP2 | Residential | Planning Consent | Submit planning application as per settlement text and taking into account design principles, including any technical assessments required. | Developer | MC Dev Mgt | Site remains vacant, looking to identify current owner.
Elgin | OPP3 | Residential or commercial | Planning Consent | Submit planning application as per settlement text and taking into account design principles, including any technical assessments required. | Developer | MC Dev Mgt | Planning consent on part of site to build 15 new flats and convert sawmill to four flats (10/00343/APP). Site cleared.
Elgin | OPP4 | Residential, industrial, commercial or retail use | Planning Consent | Submit planning application as per settlement text and taking into account design principles, including any technical assessments required. | Developer | MC Dev Mgt | Site remains vacant, looking to identify current owner.
Elgin | OPP5 | Industrial, business, office, distribution, retail | Planning Consent | Submit planning application as per settlement text and taking into account design principles, including any technical assessments required. | Developer | MC Dev Mgt | Site continues to be used for Saturday Market. Application for supermarket was withdrawn in March 2014. Planning permission in principle application for proposed mixed use development submitted in January 2017 with a decision still pending.
Elgin | OPP6 | Residential, office or community facilities. | Planning Consent | Submit planning application as per settlement text and taking into account design principles, including any technical assessments required. | Developer | MC Dev Mgt | NHS continue to occupy buildings.
Elgin | OPP7 | Residential | Planning Consent | Submit planning application as per settlement text and taking into account design principles, including any technical assessments required. | Developer | MC Dev Mgt | TPO put in place to protect trees within the site boundaries. Site purchased by MC Housing.
Elgin | CF2 | Recreational Uses | Access/Programming | Land within site safeguarded for TSP 24. | MC Dev Plans | MC Trans | 15/00607/APP permitted for the permanent deposit of excavated material for the construction of the new Elgin High School. This site is now being considered as part of the Bilbohall masterplan.
Elgin | CF4 | Elgin High School | Planning Consent | Submit planning application as per settlement text and taking into account design principles, including any technical assessments required. | Developer | MC Dev Mgt | Planning consent approved for new secondary school 14/01618/APP and construction has commenced. | C
Elgin | Lossie Green |  | Development Brief required | Lossie Green Development Brief is an action of the Moray Economic Strategy. This action is associated with other actions including Town Hall feasibility study, bus station relocation, Lossie Green multi storey car park and Alexandra Road improvements. Action will be taken forward by one of the Moray Economic Strategy Theme Groups which is accountable to the Moray Economic Partnership and Moray Community Planning Partnership. Further details of this action are contained within the Moray Economic Strategy Action Plan. | See Moray Economic Strategy action plan |  | Central Elgin Regeneration Public Design Charrette 2015 includes projects within the Lossie Green area. The Charrette report includes actions which identify projects for implementation over the next 10 years. The emerging masterplan requires to be honed and refined further. A development appraisal of proposals concluded that in current market conditions the Lossie Green masterplan would require to be a public sector led economic development and regeneration project.
Elgin | Town Centre |  | Town Centre | The Elgin High Street First Actions are actions of the Moray Economic Strategy and action will be taken forward by one of it's Theme Groups which is accountable to the Moray Economic Partnership and Moray Community Planning Partnership. Further details of this action are contained within the Moray Economic Strategy Action Plan. | See Moray Economic Strategy action plan |  | Many of the Elgin High Street First Actions were considered in the Central Elgin Regeneration Public Design Charrette 2015. The Charrette report includes action programmes which identifies projects for implementation over the next 10 years. Priority actions are being progressed and an annual summary report will be reported to the Economic Development and Infrastructure Committee.
Elgin | ENV10 | Proposed TPO | Tree Preservation Order | Proposed TPO at Pluscarden Road. | MC Dev Plan | MC Legal | TPO confirmed following agreement at Planning and Regulatory Services Committee on 23 February 2016 | C
Elgin | CA | Conservation Area | Built Heritage | A Conservation Area Regeneration Scheme has been developed in Elgin High Street Conservation Area. | MC Economic Development | Building owners | CARS scheme launched August 2013. To date the Elgin CARS Management Group has awarded a total of £482,127.84 in grants towards improvement works costing £1,061,613.80.Interest in restoring upper storeys and recived expressions of interest in vacant properties. Over 100 people have benefited from training workshops and seminars. The CARS scheme will continue to run until March 2018
Elgin | Cemetery Search |  | Cemetery | Moray Council Lands and parks working towards identifying cemetery sites for the next plan in consultation with other services. | MC Lands and Parks | MC Estates, MC Dev Plans | A site for a new Elgin Cemetery is identified within the Elgin South Masterplan.

## Findhorn-Findochty
Findhorn
Cross Reference to Essential Infrastructure Actions : EI2 (WTW), EI8 (WWTW)
Settlement | Site Reference | Allocation | Constraint/Key Infrastructure | Actions | Responsible/ Lead | Other Partners | Timescale/Progress
Findhorn | R1 | 5 houses | Planning consent | Submit planning application as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt | 14/00869/APP for 5 houses granted July 2014. Site cleared with development progressing.
Findhorn | R2 |  | N/A | Planning consent granted. |  |  | Under construction. 25 built and 15 to be completed. Small scale business units have also been completed within this site. | C
Findhorn | OPP1 | Redevelopment and expansion of existing activities | Planning consent | Submit planning application as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt | No proposals brought forward to date.
Findochty
Cross Reference to Essential Infrastructure Actions : EI3 (WW), EI7 (WWTW)
Settlement | Site Reference | Allocation | Constraint/Key Infrastructure | Actions | Responsible/ Lead | Other Partners | Timescale/Progress
Findochty | R1 | 35 houses | Planning consent | Submit planning application as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt | No proposals brought forward to date.
Findochty | R2 | 20 houses | Planning consent | Submit planning application as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt | No proposals brought forward to date.
Findochty | OPP1 | Several alternative uses | Planning consent | Submit planning application as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt | 15/00632/APP to convert disused net store to residential permitted May 2015. No proposals brought forward on remainder of OPP1 site.

## Fochabers
Fochabers
Cross Reference to Essential Infrastructure Actions : EI1 (WTW), EI9 (WWTW), EI21 (TSP's), EI25 (A96)
Settlement | Site Reference | Allocation | Constraint/Key Infrastructure | Actions | Responsible/ Lead | Other Partners | Timescale/Progress
Fochabers | R1 | 50 houses | Planning consent | Submit planning application as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt | 15/00244/APP for 49 houses approved November 2015. Development has not started | C
|  |  | Access | Co-ordinated action required to deliver two accesses for site R1 and R2. Access provision to consider LONG. Transport assessment required. Early discussions with Moray Council Transportation. Roads Drainage Assessment required. | Developer | MC Trans
Fochabers | R2 | 50 houses | Planning consent | Submit planning application as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt | Approved layout for site R1 allows for two accesses into R2. Site R2 should not commence until 75% of R1 is complete.
|  |  | Access | Co-ordinated action required to deliver two accesses for site R1 and R2. Access provision to consider LONG. Transport assessment required. Early discussions with Moray Council Transportation. Roads Drainage Assessment required. | Developer | MC Trans
|  |  | Programming | Site R1 to be 75% complete before development can commence on R2. | MC Dev Plans
Fochabers | R3 | 30 houses | Planning consent | Submit planning application as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt | Planning Application (16/00308/APP) for 42 units granted. Development onsite has begun.
Fochabers | LONG |  | Access | Co-ordinated action required to deliver two accesses for site R1 and R2. Access provision to consider LONG. Transport assessment required. Early discussions with Moray Council Transportation. Roads Drainage Assessment required. | Developer | MC Trans | Beyond plan period
|  |  | Programming | Release "LONG" if triggers are met. | MC Dev Plans
Fochabers | OPP1 | Redevelopment, potential for residential | Planning consent | Submit planning application as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt | 15/00207/APP to demolish showroom garage and replace this with a retail and residential development approved March 2015. Development commenced. | C
Fochabers | OPP2 | Residential | Planning consent | Submit planning application as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt | No proposals brought forward to date.
Fochabers | OPP3 | Business, commercial or residential | Planning consent | Submit planning application as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt | No proposals brought forward to date.
Fochabers | OPP4 | Various alternative uses | N/A | Consent for petrol filling station. | Developer | MC Dev Mgt | 12/00070/APP to erect car sales showroom and adjoining garage. Buildings built. | C

## Forres
Forres
Cross Reference to Essential Infrastructure Actions : EI2 (WTW), EI8 (WWTW), EI21 (TSP's), EI22 (Active Travel Audit), EI25 (A96)
Settlement | Site Reference | Allocation | Constraint/Key Infrastructure | Actions | Responsible/ Lead | Other Partners | Timescale/Progress
Forres | R1 | 85 houses | Planning consent | Submit planning application as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt | No proposals brought forward to date. Early engagement undertaken with developer to establish development principles.
Forres | R2 |  | N/A | Consent granted and under construction. |  |  | 71 units built. Springfield currently completing development of site under consented application 07/02414/FUL. | C
Forres | R3 |  | N/A | Masterplan in place and first phase under construction. |  |  | 93 units built. Springfield are currently completing the first phase of development under consented application 12/01110/APP. Application 16/00743/APP for 120 dwellings has been approved. | C
Forres | R4 | 440 houses | Planning consent | Submit planning application as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt | Planning consent granted for 229 units in July 2015 through application 09/02364/APP.
|  |  | Joint masterplan required R4, BP2, LONG1 | Prepare framework for preparation of Masterplan in consultation with other Council services, Key Agencies and other relevant consultees. Engage with landowner/developer. | MC Dev Plans | Landowner/ Developer, MC Dev Mgt, MC Trans, MC Education, other Council Services, Scottish Water, SEPA, SNH
|  |  |  | Prepare and consult on masterplan. Continue dialogue and work collaboratively with Moray Council, Key Agencies, and other relevant consultees as masterplan evolves. | Landowner/ Developer | MC Dev Plans, MC Dev Mgt, MC Trans, MC Education, other Council Services, Scottish Water, SEPA, SNH
Forres | R5 | 13 houses | N/A | Consent granted and under construction. |  |  | Planning consent granted in February 2014 for 16 units under application 08/00576/FUL. | C
Forres | R6 | 40 houses | Planning consent | Submit planning application as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt | Dallas Dhu masterplan for sites R6, R10 and LONG2 approved in May 2017.
|  |  | Joint masterplan required R6, R10, LONG 2, ENV10 | Prepare framework for preparation of Masterplan in consultation with other Council services, Key Agencies and other relevant consultees. Engage with landowner/developer. | MC Dev Plans | Landowner/ Developer, MC Dev Mgt, MC Trans, MC Education, other Council Services, Scottish Water, SEPA, SNH
|  |  |  | Prepare and consult on masterplan. Continue dialogue and work collaboratively with Moray Council, Key Agencies, and other relevant consultees as masterplan evolves. | Landowner/ Developer | MC Dev Plans, MC Dev Mgt, MC Trans, MC Education, other Council Services, Scottish Water, SEPA, SNH
Forres | R7 |  | N/A | Consent granted and under construction. |  |  | Development of site complete | C
Forres | R8 | 5 houses | Planning consent | Submit planning application as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt | No proposals brought forward to date.
Forres | R9 | 25 houses | Planning consent | Submit planning application as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt | No proposals brought forward to date.
Forres | R10 | 60 houses | Planning consent | Submit planning application as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt | Dallas Dhu masterplan for sites R6, R10 and LONG2 approved in May 2017.
|  |  | Joint masterplan required R6, R10, LONG 2, ENV11 | Prepare framework for preparation of Masterplan in consultation with other Council services, Key Agencies and other relevant consultees. Engage with landowner/developer. | MC Dev Plans | Landowner/ Developer, MC Dev Mgt, MC Trans, MC Education, other Council Services, Scottish Water, SEPA, SNH
|  |  |  | Prepare and consult on masterplan. Continue dialogue and work collaboratively with Moray Council, Key Agencies, and other relevant consultees as masterplan evolves. | Landowner/ Developer | MC Dev Plans, MC Dev Mgt, MC Trans, MC Education, other Council Services, Scottish Water, SEPA, SNH
Forres | R11 | 40 houses | Planning consent | Submit planning application as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt | The site is no longer constrained as the Flood Alleviation Scheme is now complete and the site is available to be developed. A development brief has been prepared to set out the design standards for future developments of the site.
|  |  | Programming | Site embargoed from development until Flood Alleviation Scheme complete. | MC Flood | MC Dev Mgt
Forres | OPP1 | Residential, commercial, industrial or retail | N/A | Outline consent for larger site that includes OPP1for food and non food retail uses. |  |  | Outline planning permission granted for redevelopment of site as part of a wider retail development. PAN submitted for 80 affordable units 16/00740/PAN.
Forres | OPP2 | Retail, residential | Planning consent | Submit planning application as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt | No proposals brought forward to date.
Forres | OPP3 | Residential or business | Planning consent | Submit planning application as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt | Development of 12 affordable houses/flats approved in December 2015. Site has since been cleared ready for development to take place. | C
Forres | OPP4 | Residential or business | Planning consent | Submit planning application as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt | No proposals brought forward to date.
Forres | OPP5 | Health care, residential or business | Planning consent | Submit planning application as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt | No proposals brought forward to date. NHS still occupying the buildings on the site
Forres | OPP6 | Residential | Planning consent | Submit planning application as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt | No proposals brought forward to date.
Forres | OPP7 |  | Planning consent | Submit planning application as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt | Planning consent for demolition of existing building and development of 24 flats granted through application 08/01954/FUL and extended through application 13/00347/APP.
Forres | OPP8 | Residential and small scale business uses | Planning consent | Submit planning application as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt | No proposals brought forward to date.
Forres | I6 |  | Planning consent | Submit planning application as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt | 15/02196/APP for new road link between A96 and Waterford Road approved April 2016. Proposals for new train station. Review allocation in LDP review.
Forres | I7 |  | Planning consent | Submit planning application as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt | No proposals brought forward to date. Site currently in use as a commercial tree nursery.
|  |  | Joint Masterplan required I7 and I8 | Prepare framework for preparation of Masterplan in consultation with other Council services, Key Agencies and other relevant consultees. Engage with landowner/developer. | MC Dev Plans | Landowner/ Developer, MC Dev Mgt, MC Trans, MC Education, other Council Services, Scottish Water, SEPA
|  |  |  | Prepare and consult on masterplan. Continue dialogue and work collaboratively with Moray Council, Key Agencies, and other relevant consultees as masterplan evolves. | Landowner/ Developer | MC Dev Plans, MC Dev Mgt, MC Trans, MC Education, other Council Services, Scottish Water, SEPA
Forres | I8 |  | Planning consent | Submit planning application as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt | No proposals brought forward to date.
|  |  | Joint Masterplan required I7 and I8 | Prepare framework for preparation of Masterplan in consultation with other Council services, Key Agencies and other relevant consultees. Engage with landowner/developer. | MC Dev Plans | Landowner/ Developer, MC Dev Mgt, MC Trans, MC Education, other Council Services, Scottish Water, SEPA
|  |  |  | Prepare and consult on masterplan. Continue dialogue and work collaboratively with Moray Council, Key Agencies, and other relevant consultees as masterplan evolves. | Landowner/ Developer | MC Dev Plans, MC Dev Mgt, MC Trans, MC Education, other Council Services, Scottish Water, SEPA
|  |  | Access | New access required. | Developer, MC Trans
Forres | BP2 |  | Planning consent | Submit planning application as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt | No planning consent to date.
|  |  | Joint masterplan required R4, BP2, LONG1 | Prepare framework for preparation of Masterplan in consultation with other Council services, Key Agencies and other relevant consultees. Engage with landowner/developer. | MC Dev Plans | Landowner/ Developer, MC Dev Mgt, MC Trans, MC Education, other Council Services, Scottish Water, SEPA, SNH
|  |  |  | Prepare and consult on masterplan. Continue dialogue and work collaboratively with Moray Council, Key Agencies, and other relevant consultees as masterplan evolves. | Landowner/ Developer | MC Dev Plans, MC Dev Mgt, MC Trans, MC Education, other Council Services, Scottish Water, SEPA, SNH
Forres | LONG 1 |  | Joint masterplan required R4, BP2, LONG1 | Prepare framework for preparation of Masterplan in consultation with other Council services, Key Agencies and other relevant consultees. Engage with landowner/developer. | MC Dev Plans | Landowner/ Developer, MC Dev Mgt, MC Trans, MC Education, other Council Services, Scottish Water, SEPA, SNH | No proposals brought forward to date. Development of the site is beyond the plan period.
|  |  |  | Prepare and consult on masterplan. Continue dialogue and work collaboratively with Moray Council, Key Agencies, and other relevant consultees as masterplan evolves. | Landowner/ Developer | MC Dev Plans, MC Dev Mgt, MC Trans, MC Education, other Council Services, Scottish Water, SEPA, SNH
|  |  | Programming | Release "LONG" if triggers are met. | MC Dev Plans
Forres | LONG2 |  | Advance Planting | Planting required to establish context and setting for new development. Planting prior to applying for planning permission. Early discussion with MC Dev Plans to agree requirements. | Developer | MC Dev Plans, MC Dev Mgt | Dallas Dhu masterplan for sites R6, R10 and LONG2 approved in May 2017.
Forres | LONG 2 |  | Joint masterplan required R6, R10, LONG 2, ENV12 | Prepare framework for preparation of Masterplan in consultation with other Council services, Key Agencies and other relevant consultees. Engage with landowner/developer. | MC Dev Plans | Landowner/ Developer, MC Dev Mgt, MC Trans, MC Education, other Council Services, Scottish Water, SEPA, SNH
|  |  |  | Prepare and consult on masterplan. Continue dialogue and work collaboratively with Moray Council, Key Agencies, and other relevant consultees as masterplan evolves. | Landowner/ Developer | MC Dev Plans, MC Dev Mgt, MC Trans, MC Education, other Council Services, Scottish Water, SEPA, SNH
|  |  | Programming | Release "LONG" if triggers are met. | MC Dev Plans
Forres | LONG 3 |  | Programming | Release "LONG" if triggers are met. | MC Dev Plans |  | Beyond plan period
Forres | ENV10 | Chapelton/Dallas Dhu | Joint masterplan required R6, R10, LONG 2, ENV15 | Prepare framework for preparation of Masterplan in consultation with other Council services, Key Agencies and other relevant consultees. Engage with landowner/developer. | MC Dev Plans | Landowner/ Developer, MC Dev Mgt, MC Trans, MC Education, other Council Services, Scottish Water, SEPA, SNH | Dallas Dhu masterplan for sites R6, R10 and LONG2 approved in May 2017.
|  |  |  | Prepare and consult on masterplan. Continue dialogue and work collaboratively with Moray Council, Key Agencies, and other relevant consultees as masterplan evolves. | Landowner/ Developer | MC Dev Plans, MC Dev Mgt, MC Trans, MC Education, other Council Services, Scottish Water, SEPA, SNH
Forres | ENV10 | High Street Public Realm | Funding | Investigate potential funding opportunities. | MC Dev Plans, MC Economic Dev |  | A Conservation Are Appraisal, Management, Action and Interpretation plan have been completed. Whilst these demonstrated that a Forres Conservation Area Regeneration Scheme would be worthwhile it was agreed by The Moray Council on 29 June 2015 that the project is not affordable in the Council's current financial position and should not be progressed.
Forres | FA2 |  | Gateway | Investigate and promote recreational woodland on west side of Forres. | MC Dev Plans | MC Flood | Investigations have been carried out into tree planting being provided for through the compensatory planting agreement with the woodland trust. However, investigations have concluded that planting within the flood plain area is discouraged.

## Garmouth- Hopeman
Garmouth
Cross Reference to Essential Infrastructure Actions : EI1 (WTW), EI16 (WWTW)
Settlement | Site Reference | Allocation | Constraint/Key Infrastructure | Actions | Responsible/ Lead | Other Partners | Timescale/Progress
Garmouth | R1 | 10 houses | Planning consent | Submit planning application as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt | No proposals brought forward to date.
Hopeman
Cross Reference to Essential Infrastructure Actions : EI2 (WTW), EI6 (WWTW)
Settlement | Site Reference | Allocation | Constraint/Key Infrastructure | Actions | Responsible/ Lead | Other Partners | Timescale/Progress
Hopeman | R1 (+LONG) | 25 houses (+30 LONG) | Masterplan required | Prepare framework for preparation of Masterplan in consultation with other Council services, Key Agencies and other relevant consultees. Engage with landowner/developer. | MC Dev Plans | Landowner/ Developer, MC Dev Mgt, MC Trans, MC Education, other Council Services, Scottish Water, SEPA | Development Brief has been completed by MC Dev Plans to set out the design standards for future developments of the site.
|  |  |  | Prepare and consult on masterplan. Continue dialogue and work collaboratively with Moray Council, Key Agencies, and other relevant consultees as masterplan evolves. | Landowner/ Developer | MC Dev Plans, MC Dev Mgt, MC Trans, MC Education, other Council Services, Scottish Water, SEPA
|  |  | Planning consent | Submit planning application as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt.
|  |  | Access | Suitable visibility splays onto B9040 and link road between the B9040 and Manse Road required. | Developer, MC Trans
Hopeman | LONG |  | Programming | Release "LONG" if triggers are met. | MC Dev Plans |  | Beyond plan period

## Keith
Keith
Cross Reference to Essential Infrastructure Actions : EI5 (WTW), EI17 (WWTW), EI21 (TSP's), EI22 (Active Travel Audit), EI25 (A96)
Settlement | Site Reference | Allocation | Constraint/Key Infrastructure | Actions | Responsible/ Lead | Other Partners | Timescale/Progress
Keith | R1 |  | N/A | Planning consent granted and partially developed | Developer | MC Dev Mgt | Being developed as single plots . One completed, one consented. | C
Keith | R2 | 25 houses | N/A | Planning consent granted and partially developed | Developer | MC Dev Mgt | Development completed. | C
Keith | R3 | 40 houses | Planning consent | Submit planning application for the whole site as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt | No individual houses will be approved until an overall and comprehensive layout covering the whole of the site has been submitted and approved. Planning application for single plot in 2015 refused on this basis.
Keith | R4 | 6 houses | Planning consent | Submit planning application for the whole site as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt | No proposals brought forward to date.
Keith | R5 | 11 houses | Planning consent | Submit planning application for the whole site as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt | Application 11/00290/APP refused in 2012. No new proposals brought forward to date.
Keith | R6 | 60 houses | Planning consent | Submit planning application for the whole site as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt | 10/01492/APP approved September 2013 for 76 houses. Planning application (17/00009/APP) for 90 affordable houses approved in May 2017.
|  |  | Access | Joint consideration required for access arrangements for R6 and R7. Early discussion with MC Trans required. | Developer | MC Trans
Keith | R7 | 200 houses | Planning consent | Submit planning application for the whole site as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt | No proposals brought forward to date.
|  |  | Access | Joint consideration required for access arrangements for R6 and R7. Early discussion with MC Trans required. | Developer | MC Trans
Keith | R8 | 85 houses | Planning consent | Submit planning application for the whole site as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt | Revised application approved September 2014. Under construction. | C
Keith | R9 | 6 houses | Planning consent | Submit planning application for the whole site as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt | No proposals brought forward to date.
Keith | R10 | 5 houses | Planning consent | Submit planning application for the whole site as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt | 15/00523/APP for one house approved May 2015. Development almost complete.
|  |  | Access | No more than 2 houses will be permitted using the existing track in its present condition. Remaining housing requires confirmation that a road to adoptable standard could be delivered and third party land constraints could be overcome. | Developer | MC Trans
Keith | LONG | 85 houses | Programming | "LONG" released if triggers met. | MC Dev Plans |  | Beyond plan period
Keith | I1 |  | Planning consent | Submit planning application for the whole site as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt | Site fully occupied. Two industrial units completed in 2014 are now let/occupied. | C
Keith | I2 |  | Planning consent | Submit planning application for the whole site as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt | Phase 1 fully occupied, phase 2 site serviced. | C
Keith | I3 | 1.62ha | Planning consent | Submit planning application for the whole site as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt | 12/01683/APP for industrial (class 5 and 6) approved April 2013 on part of site. No construction to date.
Keith | I4 |  | Planning consent | Submit planning application for the whole site as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt | Site part developed, including as building merchant. No proposals brought forward to date. 1.64ha available.
|  |  | Access and overhead cables | SE of site constrained by road access and overhead cables. Identify solutions to overcome these constraints or the extent to which the site can be developed within these constraints. | Developer | MC Dev Plans, MC Trans, Utility provider
Keith | BP1 | 1.5 ha | Planning consent | Submit planning application for the whole site as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt | No proposals brought forward to date.
Keith | OPP1 | Redevelopment | Planning consent | Submit planning application for the whole site as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt | Planning application (17/00314/APP) for a single house approved.
|  |  | Access | Visibility onto A96 constrains possible uses. Early discussion with Transport Scotland required. | Developer | Transport Scotland
Keith | OPP2 | Residential or business use | Planning consent | Submit planning application for the whole site as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt | Former school now occupied by Stagestars Scotland
|  |  | Access | Visibility onto A96 constrains possible uses. Early discussion with Transport Scotland required. | Developer | Transport Scotland
Keith | OPP3 | Residential or business use | Planning consent | Submit planning application for the whole site as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt | 15/00998/APP for 12 houses approved July 2015.
Keith | OPP4 | Redevelopment | Planning consent | Submit planning application for the whole site as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt | 13/01769/APP for housing approved February 2014. A detailed application still requires to be submitted.
Keith | T1 | Tourism | Enhance role of tourism | Signature visitor facilities are an action of the Moray Economic Strategy and action will be taken forward by one of it's Theme Groups which is accountable to the Moray Economic Partnership and Moray Community Planning Partnership. Further details of this action are contained within the Moray Economic Strategy Action Plan. | See Moray Economic Strategy action plan |  | A refresh of the Moray Economic Strategy is being carried out this financial year (2017/18) and will include an update on actions.
Keith | CA | Conservation Area | Built Environment | A Conservation Area Regeneration Scheme has been developed in Keith. | MC Economic Dev | Building owners | CARS project completed in March 2016, and around £2 million has been invested in the Conservation Area as a result. The scheme has also been successful in reducing shop vacancies and encouraging start up. It also had a well attended program of training courses. | C

## Kinloss-Lhanbryde
Kinloss
Cross Reference to Essential Infrastructure Actions : EI2 (WTW), EI8 (WWTW)
Settlement | Site Reference | Allocation | Constraint/Key Infrastructure | Actions | Responsible/ Lead | Other Partners | Timescale/Progress
Kinloss | R1 | 6 houses | Planning consent | Submit planning application as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt | Application 15/01605/PPP under consideration for 6 plots.
Kinloss | R2 |  | N/A | Planning consent granted and under construction. |  |  | 1 house not built, 7 houses completed. | C
Kinloss | R3 | 6 houses | N/A | Planning consent granted. |  |  | Application 16/00286/APP for renewal of consent for 6 houses withdrawn.
Kinloss | R4 | 25 houses | Planning consent | Submit planning application as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt | No proposals brought forward to date.
Kinloss | OPP1 | Business, tourism | Planning consent | Submit planning application as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt | No proposals brought forward to date.
Lhanbryde
Cross Reference to Essential Infrastructure Actions : EI1 (WTW), EI6 (WWTW)
Settlement | Site Reference | Allocation | Constraint/Key Infrastructure | Actions | Responsible/ Lead | Other Partners | Timescale/Progress
Lhanbryde | R1 | 65 houses | Planning consent | Submit planning application as per settlement text and design principles, including any technical assessments required. | Developer | MC Dev Mgt | No proposals brought forward to date.
Lhanbryde | OPP1 | Community uses, business, industrial, residential or cemetery | Planning consent | Submit planning application as per settlement text and design principles, including any technical assessments required. | Developer | MC Dev Mgt | Consent on part of site for housing for people with complex needs (15/02009/APP). Construction has commenced.
|  |  | Access | Mitigation measures for any development impact identified on the St Andrews Road/Garmouth Road junction will be required. Early discussion with MC Trans required. | Developer | MC Trans

## Lossiemouth
Lossiemouth
Cross Reference to Essential Infrastructure Actions : EI2 (WTW), EI6 (WWTW), EI21 (TSP's)
Settlement | Site Reference | Allocation | Constraint/Key Infrastructure | Actions | Responsible/ Lead | Other Partners | Timescale/Progress
Lossiemouth | R1 | 250 houses | Planning consent | Submit planning application as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt | 14/01468/APP for 278 approved.
|  |  | Ministry of Defence Safeguarding | Consultation required with Defence Infrastructure Organisation Safeguarding Department to establish the extent to which the site can be developed. | Developer, MC Dev Plans, MOD DIO | MC Dev Mgt
Lossiemouth | R2 | 5 houses | Planning consent | Submit planning application as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt | 2 houses complete. 3 have consent. | C
|  |  | Ministry of Defence Safeguarding | Consultation required with Defence Infrastructure Organisation Safeguarding Department to establish the extent to which the site can be developed. | Developer, MC Dev Mgt, MC Dev Plans, MOD DIO
Lossiemouth | R3 | 60 houses | N/A | Planning consent granted and under construction. |  |  | Consent 08/01685/APP and 11/01215/APP for total of 67 units. Construction continues to progress on site. | C
Lossiemouth | OPP1 | Industrial, business and retail | Planning consent | Submit planning application as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt | No proposals brought forward to date. Consent for supermarket (07/02606/FUL) now lapsed.
|  |  | Ministry of Defence Safeguarding | Consultation required with Defence Infrastructure Organisation Safeguarding Department to establish the extent to which the site can be developed. | Developer, MC Dev Mgt, MC Dev Plans, MOD DIO
|  |  | Development Brief required | Prepare and publish Development Brief in consultation with landowner/developer, other Council Services, Key Agencies and other relevant consultees. | MC Dev Plans | Landowner/ Developer, MC Dev Mgt, MC Trans, other Council, Services Scottish Water, SEPA
Lossiemouth | T2 | Caravan Park extension | Planning consent | Submit planning application as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt | No proposals brought forward to date.
Lossiemouth | ENV10 | Playing field, parkland | Sports facilities | Investigate potential for sports facilities. | MC Education | MC Dev Plans | Site to be reviewed through Open Space Strategy preparation.

## Mosstodloch-Newmill-Portgordon
Mosstodloch
Cross Reference to Essential Infrastructure Actions : EI1 (WTW), EI9 (WWTW), EI21 (TSP's), EI25 (A96)
Settlement | Site Reference | Allocation | Constraint/Key Infrastructure | Actions | Responsible/ Lead | Other Partners | Timescale/Progress
Mosstodloch | R1 | 50 houses | N/A | Planning consent granted. |  |  | Consent for 59 homes 10/01267/APP approved 08/02/13. Application 16/00083/APP to vary conditions approved.
Mosstodloch | R2 | 60 houses | Planning consent | Submit planning application as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt. | No proposals brought forward to date.
Mosstodloch | I2 | Expansion of Baxter's | Planning consent | Submit planning application as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt. | No proposals brought forward to date. Site is primarily to allow expansion of Baxter's if required.
Mosstodloch | I3 | 9.9ha | Planning consent | Submit planning application as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt. | No proposals brought forward to date. Site primarily allocated as a contingency should any existing large business need to expand or relocate.
|  |  | Design/Layout principles | Prepare framework for development in consultation with other Council services, Key Agencies and other relevant consultees. Engage with landowner/developer. | MC Dev Plans | Landowner/ Developer, MC Dev Mgt, MC Trans, MC Education, other Council Services, Scottish Water, SEPA, SNH
Newmill
Cross Reference to Essential Infrastructure Actions : EI5 (WTW), EI17 (WWTW)
Settlement | Site Reference | Allocation | Constraint/Key Infrastructure | Actions | Responsible/ Lead | Other Partners | Timescale/Progress
Newmill | R1 | 6 to 10 houses | Planning consent | Submit planning application as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt | No proposals brought forward to date.
Newmill | OPP1 | Residential | Planning consent | Submit planning application as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt | No proposals brought forward to date.
Portgordon
Cross Reference to Essential Infrastructure Actions : EI1 (WTW), EI7 (WWTW)
Settlement | Site Reference | Allocation | Constraint/Key Infrastructure | Actions | Responsible/ Lead | Other Partners | Timescale/Progress
Portgordon | R1 | 40 houses | Planning consent | Submit planning application as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt | No proposals brought forward to date.
Portgordon | R2 | 55 houses | Planning consent | Submit planning application as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt | No proposals brought forward to date.

## Portnockie-Rafford
Portknockie
Cross Reference to Essential Infrastructure Actions : EI3 (WTW), EI7 (WWTW)
Settlement | Site Reference | Allocation | Constraint/Key Infrastructure | Actions | Responsible/ Lead | Other Partners | Timescale/Progress
Portknockie | R1 | 50 houses | Planning consent | Submit planning application as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt | No proposals brought forward to date.
Rafford
Cross Reference to Essential Infrastructure Actions : EI4 (WTW)
Settlement | Site Reference | Allocation | Constraint/Key Infrastructure | Actions | Responsible/ Lead | Other Partners | Timescale/Progress
Rafford | R1 | 12 houses | Planning consent | Submit planning application as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt | No proposals brought forward to date. No indication of owner progressing or marketing site for development.
|  |  | Drainage arrangements | Early discussion with Scottish Water regarding existing septic tank capacity and alternative options for provision. | Developer | Scottish Water

## Rothes-Rothiemay
Rothes
Cross Reference to Essential Infrastructure Actions : EI1 (WTW), EI18 (WWTW)
Settlement | Site Reference | Allocation | Constraint/Key Infrastructure | Actions | Responsible/ Lead | Other Partners | Timescale/Progress
Rothes | R1 | 30 houses | Planning consent | Submit planning application as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt. | No proposals brought forward to date. Landownership issues.
Rothes | R2 | 40 houses | Planning consent | Submit planning application as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt. | No proposals brought forward to date.
Rothes | OPP1 | Industrial or mixed use housing/ industrial | Planning consent | Submit planning application as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt. | No proposals brought forward to date. Ownership constraint
|  | Industrial or mixed use housing/ industrial | Development Brief required | Prepare and publish Development Brief in consultation with landowner/developer, other Council Services, Key Agencies and other relevant consultees. | MC Dev Plans | Landowner/ Developer, MC Dev Mgt, MC Trans, other Council, Services Scottish Water, SEPA, SNH
Rothes | OPP2 | Residential or commercial | Planning consent | Submit planning application as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt. | No proposals brought forward to date.
Rothes | I1 | Lorry park | Planning consent | Submit planning application as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt. | No proposals brought forward to date.
Rothiemay
Cross Reference to Essential Infrastructure Actions : EI3 (WTW), EI19 (WWTW)
Settlement | Site Reference | Allocation | Constraint/Key Infrastructure | Actions | Responsible/ Lead | Other Partners | Timescale/Progress
Rothiemay | R1 | 15 houses | Planning consent | Submit application as per settlement text, including technical assessments required. | Developer | MC Dev Mgt | Planning consent granted for 11 houses 14/01431/AMC, 12 November 2014.
|  |  | Limited waste water capacity | Moray Council to work with Scottish Water to establish what is needed for development proposals. | MC Dev Plans | Scottish Water
Rothiemay | R2 | 5 houses | Planning consent | Submit application as per settlement text, including technical assessments required. | Developer | MC Dev Mgt | No proposals brought forward to date.
|  |  | Limited waste water capacity | Moray Council to work with Scottish Water to establish what is needed for development proposals. | MC Dev Plans | Scottish Water
Rothiemay | R3 | 10 houses | Planning consent | Submit application as per settlement text, including technical assessments required. | Developer | MC Dev Mgt | No proposals brought forward to date.
|  |  | Limited waste water capacity | Moray Council to work with Scottish Water to establish what is needed for development proposals. | MC Dev Plans | Scottish Water

## Urquhart
Urquhart
Cross Reference to Essential Infrastructure Actions : EI1 (WTW), EI6 (WWTW)
Settlement | Site Reference | Allocation | Constraint/Key Infrastructure | Actions | Responsible/ Lead | Other Partners | Timescale/Progress
Urquhart | R1 | 10 houses | Planning consent | Submit planning application as per settlement text, including any technical assessments required. | Developer | MC Dev Mgt | Site being marketed for sale
Urquhart | LONG1 | 10 houses | Programming | Release "LONG" if triggers are met. | MC Dev Plans |  | Site being marketed for sale. Beyond plan period
Urquhart | LONG2 | 5 houses | Programming | Release "LONG" if triggers are met. | MC Dev Plans |  | Beyond plan period